## Core Modules Completed
LANE 1 — BLOCK 2 │ Rule Engine Core Module Build
Steel Detailing Desktop System · Engine Core Execution Pack · Lane 1 Block 2
|  |  | Prepared by: | Lane 1 Block 2 Agent | Date: | 2026-04-27 | v1.0
# | Module / Component | Type | Build Status | DB Dependency | Interface | Notes / Detail | Owner
── SECTION 1: CORE ENGINE MODULES ──
1 | engine_core | Orchestrator | ✅ Complete | ✅ Verified | EngineCore.run(project_id, stage) | Connects all sub-modules; manages run_id; calls rule_loader → severity_handler → blocker_registry → audit_writer; writes to validation_result and project_stage_status | Lane 1 Agent
2 | rule_loader | Data Access | ✅ Complete | ✅ Verified | RuleLoader.load_rules(stage) / load_by_layer(layer,stage) | Reads from validation_rule_master WHERE is_active=1 AND (stage_scope IS NULL OR stage_scope=?). Returns typed dicts ordered by layer, severity. | Lane 1 Agent
3 | severity_handler | Logic | ✅ Complete | ✅ Verified | SeverityHandler.record(rule, outcome) / gate_result(stage, blocker_registry) | Tracks BLOCKER/RELEASE_BLOCKER/ERROR/WARNING/INFO counts. Hard-gate enforced for S4 and S5 — any BLOCKER or RELEASE_BLOCKER fail → gate_status=BLOCKED regardless of other results. | Lane 1 Agent
4 | blocker_registry | Accumulator | ✅ Complete | ✅ Verified | BlockerRegistry.register(rule, detail) / get_all(severity) / summary() | Groups failed rules by severity into defaultdict. Provides count(), get_all(), summary() for gate result model and downstream reporting. | Lane 1 Agent
5 | audit_writer | Persistence | ✅ Complete | ✅ Verified | AuditWriter.write(event_type, summary, ...) | Inserts to audit_event_log with is_immutable=1. Accepts project_id, related_id, related_table, JSON detail payload. Returns audit_id for traceability. | Lane 1 Agent
── SECTION 2: RULE LOADING CONFIRMATION ──
C1 | Rule load from validation_rule_master | DB Read | ✅ Complete | ✅ Verified | SELECT ... WHERE is_active=1 AND (stage_scope IS NULL OR stage_scope=?) | Confirmed: query filters by stage_scope allowing NULL (global) rules. ORDER BY layer, severity ensures deterministic execution order. | Lane 1 Agent
C2 | Rule load by specific layer | DB Read | ✅ Complete | ✅ Verified | load_by_layer(layer, stage) | Allows Block 3 layer modules to pull only their ruleset without full-scan. Supports L01–L13 layer codes. | Lane 1 Agent
── SECTION 3: GATE RESULT MODEL ──
G1 | Gate result model structure | Logic | ✅ Complete | N/A | dict: gate_status, is_hard_gate, severity_counts, blocker_count, release_blocker_count, error_count, warning_count | gate_status ∈ {PASSED, OPEN, BLOCKED}. PASSED = no fails. OPEN = errors/warnings but no blockers. BLOCKED = BLOCKER or RELEASE_BLOCKER present. | Lane 1 Agent
G2 | S4 hard-gate blocking | Logic | ✅ Complete | N/A | SeverityHandler.gate_result — HARD_GATE_STAGES={'S4','S5'} | S4 and S5 unconditionally BLOCKED if any BLOCKER or RELEASE_BLOCKER fail. Cannot be overridden at engine level. | Lane 1 Agent
G3 | Gate result written to project_stage_status | DB Write | ✅ Complete | ✅ Verified | engine_core._update_stage_status() | UPSERT pattern: updates existing row or inserts new (project_id, stage) record. gate_result_json stores full snapshot for audit trail. | Lane 1 Agent
── SECTION 4: SEVERITY HANDLING ──
S1 | BLOCKER handling | Severity | ✅ Complete | ✅ Verified | severity_handler + blocker_registry | Registered in blocker_registry. Causes gate_status=BLOCKED. Hard blocks S4/S5 progression. | Lane 1 Agent
S2 | RELEASE_BLOCKER handling | Severity | ✅ Complete | ✅ Verified | severity_handler + blocker_registry | Same hard-block behavior as BLOCKER. Distinguished for reporting — marks issues that block release (IFC export / final submission) specifically. | Lane 1 Agent
S3 | ERROR handling | Severity | ✅ Complete | ✅ Verified | severity_handler | Counted in error_count. gate_status=OPEN (not hard-blocked). Flagged for user attention but does not block standard stage advancement. | Lane 1 Agent
S4 | WARNING handling | Severity | ✅ Complete | ✅ Verified | severity_handler | Counted in warning_count. Does not affect gate_status. Surfaced for advisory display only. | Lane 1 Agent
S5 | INFO handling | Severity | ✅ Complete | N/A | severity_handler | Tracked in severity_counts dict. No gate impact. Used for trace/diagnostic messages from layers. | Lane 1 Agent
BLOCK 2 STATUS SUMMARY
Total | ✅ Complete | ⚠️ Partial | ❌ Not Built | 🔁 In Progress | 🔒 Blocked | Block Status | Sign-off
15 | 15 | 0 | 0 | 0 | 0 | 🟢 GREEN | Lane 1 Block 2 Agent

## SQLite RW Dependencies
LANE 1 — BLOCK 2 │ SQLite Read / Write Dependency Matrix
Maps engine modules to their DB tables and operations
# | Module | Table | Operation | Access Type | Status | Notes | Owner
1 | rule_loader | validation_rule_master | SELECT | READ | ✅ Verified | Filters is_active=1, stage_scope. Orders by layer, severity. | Lane 1 Agent
2 | engine_core | validation_result | INSERT | WRITE | ✅ Verified | Writes one row per rule evaluated per run. run_id groups batch. | Lane 1 Agent
3 | engine_core | project_stage_status | INSERT / UPDATE | WRITE | ✅ Verified | UPSERT pattern by (project_id, stage). Stores gate_result_json snapshot. | Lane 1 Agent
4 | audit_writer | audit_event_log | INSERT | WRITE | ✅ Verified | is_immutable=1; no UPDATE/DELETE permitted. Returns audit_id. | Lane 1 Agent
5 | engine_core | project_master | SELECT | READ | ✅ Verified | Validates project_id existence before run. FK cascade guard. | Lane 1 Agent
6 | severity_handler | — | In-memory | NONE | ✅ Verified | Pure in-memory computation. No direct DB access. Receives data from rule_loader output. | Lane 1 Agent
7 | blocker_registry | — | In-memory | NONE | ✅ Verified | Accumulates fails in defaultdict. No DB I/O. Consumed by engine_core for gate update. | Lane 1 Agent