LANE 3 · BLOCK 1 AGENT UI Shell Foundation — Progress Note Ref: IFS-BUILD-OUT4-UI-20260424 ¦ Baseline: IFS-P7-UI-20260423 / MasterDB v3+ ¦ Date: 2026-04-27

# 1. UI Shell Foundation Status

| Parameter | Value |
| --- | --- |
| Document Authority | IFS-P7-UI-20260423 (FROZEN — no redesign permitted) |
| Total Shell Screens | 14 (8 primary + 6 supporting views) |
| Roles Bound | 8 — drafter ¦ checker ¦ detailing_lead ¦ design_engineer ¦ pm ¦ document_controller ¦ qc_lead ¦ it_admin |
| Live Update Method | FastAPI WebSocket — gate status, approval queue, pipeline progress |
| Blocker Badge Rule | RED header badge on EVERY project screen when Release-Blockers > 0 |
| Audit Mode | READ-ONLY — no INSERT/UPDATE/DELETE controls rendered in UI-08 |
| Override Prohibited Guard | 28 fields: no override button rendered; lock icon + tooltip displayed |
| Source/Confidence Display | Every field shows: source name, priority rank (P1–P8), confidence % |
| Shell Coding Status | APPROVED FOR CODING ✓ (UI Team Lead, 2026-04-24) |

# 2. Screens Started / Completed

| Screen ID | Screen Name | Priority | Status | Owner | Target |
| --- | --- | --- | --- | --- | --- |
| UI-01 | Project Dashboard | P1-CRITICAL | IN PROGRESS | UI Dev 1 | 2026-04-26 |
| UI-02 | Stage Status Board | P1-CRITICAL | IN PROGRESS | UI Lead | 2026-04-27 |
| UI-04 | Validation Results View | P1-CRITICAL | IN PROGRESS | UI Dev 2 | 2026-04-27 |
| UI-05 | Blocker View | P1-CRITICAL | IN PROGRESS | UI Dev 2 | 2026-04-27 |
| UI-03 | Field Population Viewer | P1-CRITICAL | QUEUED | UI Dev 1 | 2026-04-28 |
| UI-06 | Override Request View | P2-HIGH | QUEUED | UI Dev 2 | 2026-04-28 |
| UI-07 | Approval Queue | P2-HIGH | QUEUED | UI Lead | 2026-04-28 |
| UI-08 | Audit Trail Viewer | P2-HIGH | QUEUED | UI Dev 1 | 2026-04-28 |
| UI-09 | Source/Confidence Panel | P2-HIGH | QUEUED | UI Dev 2 | 2026-04-29 |
| UI-10 | Manual Review Queue | P3 | DEFERRED (Phase 5b) | UI Dev 2 | TBD |
| UI-11 | Release Control | P3 | DEFERRED (Phase 5b) | UI Lead | TBD |
| UI-12 | Benchmark Dashboard | P3 | DEFERRED | UI Dev 1 | TBD |
| UI-13 | Defect Dashboard | P3 | DEFERRED | UI Dev 2 | TBD |
| UI-14 | System Config | P3 | DEFERRED | IT Admin | TBD |

Block 1 scope covers UI-01, UI-02, UI-04, UI-05 (P1-CRITICAL core shell). UI-03, UI-06, UI-07, UI-08, UI-09 targeted for Block 2. UI-10 through UI-14 deferred pending integration layer confirmation.

# 3. Data Binding Status

## 3a. Screen → SQLite Table Bindings

| Screen | Primary Read Tables | Write Tables | Refresh Trigger | Binding Status |
| --- | --- | --- | --- | --- |
| UI-01 | project_master, project_file_registry, design_standard_master | project_master, project_file_registry, intake_sheet_registry | On file upload / project create | CONFIRMED — pending DB-INIT-001 |
| UI-02 | project_stage_status, stage_gate_master, validation_result | project_stage_status (via engine only) | WebSocket: gate_status_update | CONFIRMED — pending IV-2.0.0 WS schema |
| UI-04 | validation_result, validation_rule_master, manual_review_trigger_master | manual_review_event (trigger) | WebSocket: engine run complete | CONFIRMED — pending DB-INIT-001 |
| UI-05 | validation_result WHERE severity=Release-Blocker, override_rule_master | approval_request (override submit) | WebSocket: new blocker created | CONFIRMED — pending DB-INIT-001 |
| UI-06 | field_master, override_rule_master, field_value_store | approval_request | On submit / confirmation modal | SCHEMA VERIFIED |
| UI-07 | approval_request, approval_decision, override_rule_master | approval_decision, audit_event_log | WebSocket: new approval request | CONFIRMED — pending WS schema |
| UI-08 | audit_event_log, field_extraction_log, correction_event_log, override_event_log | — READ ONLY | On filter change / export | CONFIRMED — READ-ONLY enforced |

## 3b. Mandatory Widget Bindings (Release-Blocker Visibility)

| Widget | Location | Data Source | Status |
| --- | --- | --- | --- |
| Header Blocker Badge | Top of EVERY project screen | validation_result WHERE severity=Release-Blocker AND generation_blocked=1 | CONFIRMED ✓ |
| Stage Traffic Light | UI-02 (each S1–S10 row) | project_stage_status.gate_status | CONFIRMED ✓ |
| Override Prohibited Lock | UI-03 — 28 prohibited fields | field_master.is_override_prohibited | CONFIRMED ✓ |
| Quorum Progress Bar | UI-07 Approval Queue | approval_decision WHERE request_id=X | CONFIRMED ✓ |
| Audit Log Confirmation | UI-06, UI-07 — on action | Pre-write confirm + audit_event_log INSERT | CONFIRMED ✓ |
| Generation Block Banner | UI-04, UI-05 | validation_result WHERE generation_blocked=1 | CONFIRMED ✓ |

# 4. Blockers

| ID | Description | Owner | Target Date | Severity |
| --- | --- | --- | --- | --- |
| B-UI-01 | IV-2.0.0 Integration Layer NOT FROZEN — WebSocket event schema unconfirmed. UI-to-engine event binding contract undefined. Blocks: UI-02, UI-05, UI-07 WebSocket bindings. | Chief Architect | 2026-04-29 | BLOCKER |
| B-UI-02 | DB-INIT-001 (Output 1) must PASS before UI can bind to project_stage_status or approval_request. All SQLite read tables unavailable until schema initialized. | DB Lead | 2026-04-28 | BLOCKER |
| R-UI-01 | CCB roster NOT CONFIRMED — 3 of 8 governance seats unfilled. Approval workflow screens (UI-06, UI-07) cannot be signed off until authority established. | Program Manager | 2026-04-25 | RISK |

## 4b. Blocker Impact & Unblocked Path

| Blocker | Screens Impacted | Unblocked Path |
| --- | --- | --- |
| B-UI-01 | UI-02 (WS refresh), UI-05 (blocker push), UI-07 (approval push) | Chief Architect confirms WS event schema → UI Lead implements WebSocket bindings |
| B-UI-02 | UI-01, UI-02, UI-04, UI-05 (all SQLite reads) | DB Lead runs DB-INIT-001 → schemas confirmed → UI devs bind tables |
| R-UI-01 | UI-06, UI-07 (approval workflow sign-off) | PM confirms remaining 3 CCB seats → governance authority established |

# 5. Next Block Readiness

| # | Exit Criterion | Status | Owner |
| --- | --- | --- | --- |
| 1 | UI-01 Project Dashboard — project_master row creation confirmed; unit_system immutable lock applied | TARGET: 2026-04-26 | UI Dev 1 |
| 2 | UI-02 Stage Status Board — 10-gate traffic light display from project_stage_status confirmed correct | TARGET: 2026-04-27 | UI Lead |
| 3 | UI-02 — Header Blocker Badge renders RED + correct count on Release-Blockers > 0 | TARGET: 2026-04-27 | UI Lead |
| 4 | UI-04 Validation Results View — gate-level pass/warn/fail + blocker list + re-run trigger functional | TARGET: 2026-04-27 | UI Dev 2 |
| 5 | UI-05 Blocker View — dedicated Release-Blocker list with field, rule ID, severity, remediation path | TARGET: 2026-04-27 | UI Dev 2 |
| 6 | Role-based access control layer active — role_master lookup enforced on every screen load | TARGET: 2026-04-27 | UI Lead |
| 7 | FastAPI WebSocket endpoint active for gate status + approval queue push events | TARGET: 2026-04-27 | Backend Lead |
| 8 | UI-BOOTSTRAP-001 acceptance test passed | TARGET: 2026-04-28 | UI Lead + QA |
| 9 | B-UI-01 cleared (WS schema confirmed) to unblock Block 2 WebSocket bindings | DEPENDENCY | Chief Architect |
| 10 | B-UI-02 cleared (DB-INIT-001 passed) to unblock Block 2 SQLite read tables | DEPENDENCY | DB Lead |

BLOCK 1 → BLOCK 2 READINESS VERDICT CONDITIONAL — Block 2 entry gated on: (1) B-UI-02 cleared for SQLite table access, and (2) B-UI-01 cleared for WebSocket schema confirmation. Core shell screens UI-01, UI-02, UI-04, UI-05 may proceed to build in parallel. WebSocket-dependent refresh bindings on UI-02/05/07 to be wired only after IV-2.0.0 WS schema is frozen. Block 2 scope (UI-03, UI-06, UI-07, UI-08, UI-09) targets 2026-04-28 to 2026-04-29.

Lane 3 · Block 1 Agent  |  IFS-BUILD-OUT4-UI-20260424  |  Baseline: MasterDB v3+ · IFS-P7-UI-20260423  |  Generated: 2026-04-27