INFINITI SOLUTIONS STEEL DETAILING AUTOMATION

Phase 5 — Lane-Based Execution

END-OF-DAY CONSOLIDATED REPORT

DATE: 2026-04-27  |  BASELINE: MasterDB v3+ / MDB-3.2.0  |  CONSOLIDATION BY: Komal

| Lane 1 GREEN | Lane 2 AMBER | Lane 3 RED | Integration Hold UNCHANGED | Daily Status RED |
| --- | --- | --- | --- | --- |

1. Daily Executive Summary

Today, 2026-04-27, marked a critical build day for Phase 5. All three lanes executed under the MasterDB v3+ / MDB-3.2.0 frozen baseline. The team achieved substantial component-level progress; however, the day closes with three unresolved CRITICAL blockers concentrated in Lane 3, which hold the integration hold firmly in place and suppress overall programme status to RED.

### Key Achievements Today

- Lane 1 (Backend): Blocks 1–4 fully complete and production-ready. 57-table SQLite schema frozen, rule engine orchestrator operational, 6 core validation layers (L01–L05, L10) built and tested. No blockers.

- Lane 2 (Parser): Blocks 1–5 complete. All 8 parser adapters (P1–P8) implemented and frozen. Evidence automation framework operational (5 automated export tasks). Amber status due to 2 external blockers — both with clear owners and 24-hour target resolution.

- Lane 3 (UI/Governance): Blocks 1–3 complete at specification level. 14-screen UI shell defined, governance screens fully scoped, hold-closure gap analysis completed. Red status — 3 critical blockers active, one overdue by 2 days.

### Programme Concerns

- B-UI-02 / B-PARSER-02: DB-INIT-001 not yet run — SQLite schema not initialized. This single blocker cascades to ALL SQLite-dependent screens in Lane 3 and ALL evidence automation live tests in Lane 2.

- B-UI-01 / B-PARSER-01: IV-2.0.0 Integration Layer freeze not complete — WebSocket event schema unconfirmed, Parser-to-engine contract unsigned. Blocks 3 UI screens and all parser conflict/fallback work.

- R-UI-01: CCB roster 3/8 seats unfilled — 2 days overdue (target 2026-04-25). Gate bypass quorum physically impossible. Emergency session required today.

2. Lane 1 Status — Backend / Schema / Rule Engine

Lane 1 — Backend / Schema / Rule Engine  [GREEN]

### Completed Work

- Block 1 — SQLite Core Schema: COMPLETE. 57 tables built in strict FK dependency order. 6 immutable audit triggers. 24+ performance indexes. All PRAGMA settings configured (WAL, FK enforcement, cache). Verified against Master DB v3.0 column-for-column.

- Block 2 — Rule Engine Core: COMPLETE. engine_core, rule_loader, severity_handler, blocker_registry, audit_writer — all 5 modules operational. S4/S5 hard-gate enforcement tested. Prerequisite checking (S1–S4 before S5) confirmed. Gate result model finalized.

- Block 3 — Core Validation Layers: COMPLETE. L01 (Completeness), L02 (Data Type), L03 (Unit), L04 (Value Range), L05 (Regex), L10 (Hard Gate Enforcement) — all built and tested. Edge cases (NULL, empty strings, whitespace, boundary conditions) verified.

- Block 4 — Lane Packaging: COMPLETE. All Blocks 1–3 consolidated. No open blockers at consolidation checkpoint.

### Key Outputs Generated

| Artifact | Description | Status |
| --- | --- | --- |
| LANE1_CORRECTED_SCHEMA_FINAL_v3.sql | 70 KB, 2000+ lines, 57 tables, production-ready | COMPLETE ✅ |
| Lane1_Block1_steel_detailing.db | 11 KB live SQLite database — schema verified buildable | COMPLETE ✅ |
| README_CORRECTED_SCHEMA.md | 15 KB implementation guide with 13-step validation checklist | COMPLETE ✅ |
| Rule Engine Modules (5) | engine_core, rule_loader, severity_handler, blocker_registry, audit_writer | COMPLETE ✅ |

### Blockers

None active. SCHEMA-DB-CREATION-RED flagged as a pre-flight advisory for Block 5 — atomic transaction wrapper and post-build validation script required before seed data load. Owned by Block 5 Agent.

3. Lane 2 Status — Parser / Extraction / Evidence Automation

Lane 2 — Parser / Extraction / Evidence Automation  [AMBER]

### Completed Work

- Block 1 — Parser Framework: COMPLETE. BaseParser ABC, FieldExtraction dataclass, SourceType / ExtractionMethod / FieldStatus enums, confidence hard-cap enforcement, historical prohibition guard (P8), all 8 adapter skeletons.

- Block 2 — MBS & STAAD Adapters: COMPLETE. STAAD (P1): SP-01 through SP-09 — bolt, section, support, connection parsing. MBS (P2): MP-01 through MP-07 — XML + text fallback, bay/envelope/connection/sheeting. Zero fallback pollution confirmed.

- Block 3 — Evidence Automation: COMPLETE. 5 automated exports: DB snapshot, parser log, extraction log, field_value_store, validation_result. Evidence manifest. BM-001–BM-005 folder naming compliant. Guard B-PARSER-02 check implemented.

- Block 4 — Lane Packaging: COMPLETE.

- Block 5 — ETABS / Prota / PDF / Archive Adapters: COMPLETE. ETABS (P3), Prota DXF (P4), Prota PDF (P5), DWG/DXF Generic (P6), PDF Text (P7), PDF Image/OCR (P8), Archive Extractor utility — all 7 adapters production-ready and frozen.

### Key Outputs Generated

| Module | File | Priority / Status |
| --- | --- | --- |
| BaseParser + Enums | base/parser_interface.py | FROZEN ✅ |
| STAAD Adapter | staad_parser/staad_main.py | P1 — COMPLETE ✅ |
| MBS Adapter | mbs_parser/mbs_main.py | P2 — COMPLETE ✅ |
| ETABS Adapter | etabs_parser/etabs_main.py | P3 — COMPLETE ✅ |
| Prota DXF + PDF | prota_parser/prota_parser.py | P4/P5 — COMPLETE ✅ |
| DWG/DXF Generic | cad_parser/cad_main.py | P6 — COMPLETE ✅ |
| PDF Text + OCR | pdf_parser/pdf_parsers.py | P7/P8 — COMPLETE ✅ |
| Archive Extractor | archive_extractor/archive_extractor.py | UTILITY — COMPLETE ✅ |
| Evidence Exporter | evidence_automation/evidence_exporter.py | FROZEN ✅ |

### Blockers

| Blocker ID | Description | Owner | Target | Impact |
| --- | --- | --- | --- | --- |
| B-PARSER-01 | IV-2.0.0 Integration Layer NOT FROZEN. write_to_db() contract unsigned. conflict_resolver.py (C9) design blocked. | Chief Architect | 2026-04-29 | Blocks Block 6 & 7 entirely |
| B-PARSER-02 | DB-INIT-001 not run. field_value_store, extraction_log, validation_result tables missing. | DB Lead | 2026-04-28 | Blocks all 5 live evidence exports |
| R-PARSER-01 | ODA File Converter installation not verified on developer machines. | Parser Lead | 2026-04-27 | Blocks P6 adapter runtime execution |

### Next Start Point

- Block 6 (Conflict & Fallback Harness): READY — pending B-PARSER-01 clearance only. conflict_resolver.py (C9) design review required. All 7 adapter outputs (P1–P8) are correct and ready for handoff.

- Block 7 (Benchmark Evidence): PENDING B-PARSER-01. Deferred exports: audit_sample, conflict, fallback-chain, defect log, run report.

- Estimated Lane 2 full completion (Blocks 1–8): 2026-05-03 if blockers clear on schedule.

4. Lane 3 Status — UI / Governance / Hold Closure

Lane 3 — UI / Governance / Hold Closure  [RED]

### Completed Work

- Block 1 — UI Shell Foundation: COMPLETE (specification). 14-screen shell architecture defined and frozen (8 primary + 6 supporting). 8 roles mapped with RBAC enforcement (drafter, checker, detailing_lead, design_engineer, pm, document_controller, qc_lead, it_admin). SQLite data bindings confirmed. FastAPI WebSocket architecture scoped.

- Block 2 — Approval / Override / Audit Shell: COMPLETE (specification). 4 governance screens fully specified: UI-06 (Override Request), UI-07 (Approval Queue), UI-08 (Audit Trail Viewer), UI-09 (Source/Confidence Panel). Override event flow mapped end-to-end. 10 audit visibility rules defined (AUDIT-READ-001 through AUDIT-PERF-001). 100ms SLA on 10K events.

- Block 3 — Hold Closure Prep: COMPLETE (specification). 3 critical blockers with gap analysis. 6 IV-2.0.0 requirements mapped. 6 BJ-010 alignment points scoped. 8-seat CCB roster structure defined. 11 gap closure exit criteria itemized.

- 4 screens (UI-01, UI-02, UI-04, UI-05) IN PROGRESS — blocked on B-UI-02 (DB-INIT-001). 5 screens queued for Block 2. 5 deferred.

### Blockers — ALL CRITICAL

| Blocker ID | Description | Owner | Target | Severity |
| --- | --- | --- | --- | --- |
| B-UI-01 | IV-2.0.0 NOT FROZEN — WebSocket event schema unconfirmed. UI-Engine Event Binding Contract does not exist. Baseline assumed delivery by 2026-04-27; actual 2026-04-29. | Chief Architect | 2026-04-29 | CRITICAL |
| B-UI-02 | DB-INIT-001 NOT RUN — SQLite schema not initialized. ALL SQLite-dependent screens (UI-01 through UI-08) blocked. Highest-impact single blocker across all lanes. | DB Lead | 2026-04-28 | CRITICAL — HIGHEST IMPACT |
| R-UI-01 | CCB Roster: 3/8 seats UNFILLED (Design Engineer, Document Controller, Independent Reviewer). TARGET OVERDUE by 2 days (2026-04-25). Gate bypass quorum physically impossible. | Program Manager | 2026-04-28 ⚠ | CRITICAL → BLOCKER ESCALATED |

### Baseline Deviations — 2 Confirmed

DEVIATION 1: R-UI-01 — CCB roster target (2026-04-25) missed by 2 days. Was rated manageable at Block 1; now escalating to BLOCKER status. Mitigation: Emergency CCB session required EOD 2026-04-27.

DEVIATION 2: IV-2.0.0 — UI-Engine Event Binding Contract does not exist. Baseline assumed in place by 2026-04-27; actual delivery now 2026-04-29. WebSocket bindings (UI-02, UI-05, UI-07) deferred to Block 4.

### Next Start Point

- Morning standup (2026-04-28): 15-min status check — DB-INIT-001 PASS confirmation, CCB seats 06/07/08 named, WS event schema draft published.

- If B-UI-02 PASSES: Release UI-01, 02, 04, 05, 06, 07, 08 to full build simultaneously.

- UI-09 (Source/Confidence Panel): No blockers — can start immediately regardless.

- If all 3 blockers remain open at EOD 2026-04-28: Escalate to CTO; freeze approval workflow governance to Phase 5b.

5. Cross-Lane Dependency Issues

| Dependency | From Lane | To Lane(s) | Blocker Ref | Status |
| --- | --- | --- | --- | --- |
| DB-INIT-001 script execution and PASS confirmation | Lane 1 / DB Lead | Lane 2, Lane 3 | B-UI-02 / B-PARSER-02 | BLOCKED — DB Lead |
| IV-2.0.0 WS event schema freeze + Binding Contract | Lane 3 / Chief Architect | Lane 2, Lane 3 | B-UI-01 / B-PARSER-01 | BLOCKED — Chief Architect |
| FastAPI WebSocket endpoint URL + auth | Backend Lead | Lane 3 | B-UI-01 (partial) | OPEN — Backend Lead |
| conflict_resolver.py (C9) design sign-off | Lane 4 / Chief Architect | Lane 2 | B-PARSER-01 | BLOCKED — Chief Architect |
| BJ-010 table/field name diff verification | Lane 3 / DB Lead | Lane 3 | B-UI-02 (partial) | OPEN — DB Lead |
| CCB Roster complete (seats 06/07/08) | Program Manager | Lane 3 | R-UI-01 | OVERDUE — Program Manager |
| ODA File Converter installation verification | Parser Lead (self) | Lane 2 | R-PARSER-01 | OPEN — Parser Lead |

Critical observation: The DB-INIT-001 execution (DB Lead) is the single highest-impact dependency in the programme. Its clearance unblocks 8 UI screens across Lane 3 and 5 live export tests in Lane 2 simultaneously. DB Lead must treat this as a P0 priority item.

6. Open Blockers and Risks

### Open Blockers

| ID | Description | Owner | Target | Lane Impact | Severity |
| --- | --- | --- | --- | --- | --- |
| B-UI-02 / B-PARSER-02 | DB-INIT-001 not executed. SQLite schema not live. | DB Lead | 2026-04-28 | Lane 2 + Lane 3 | CRITICAL |
| B-UI-01 / B-PARSER-01 | IV-2.0.0 not frozen. WS schema + Binding Contract missing. | Chief Architect | 2026-04-29 | Lane 2 + Lane 3 | CRITICAL |
| R-PARSER-01 | ODA File Converter installation unverified. | Parser Lead | 2026-04-27 | Lane 2 | OPEN |
| SCHEMA-DB-CREATION-RED | Pre-flight advisory: atomic transaction wrapper required before Block 5. | Block 5 Agent | Before Block 5 | Lane 1 | ADVISORY |

### Risks

| Risk | Probability | Impact | Mitigation | Owner |
| --- | --- | --- | --- | --- |
| B-UI-02 slip beyond 2026-04-28 cascades all Block 2 builds; integration testing blocked | HIGH | Block 2–3 slip 2–4 days | DB Lead to treat DB-INIT-001 as P0; QA to confirm PASS immediately | DB Lead |
| CCB seats unfilled >2 days past target. Approval workflow governance sign-off on critical path | HIGH | Release gate delay 3–5 days | Program Manager to call emergency CCB session EOD 2026-04-27 | Program Manager |
| IV-2.0.0 scope expansion — additional WS event types delay UI-02/05/07 builds | MEDIUM | Block 3 extension, Block 4 start delay | Chief Architect to publish frozen schema (gates, approval, pipeline only) by 2026-04-29; no expansion | Chief Architect |
| ETABS >20% section unmapping against IS 808 catalogue | HIGH | Manual review load increases | IS808_LOOKUP_REQUIRED flag + manual review escalation | Parser Lead |
| Tesseract OCR failure on poor scans (P8 adapter) | HIGH | Historical prohibition guard critical | Confidence hard cap 75 + HISTORICAL_PROHIBITED auto-UNRESOLVED + OCR_USED_MANDATORY_REVIEW | Parser Lead |
| SQLite audit_event_log 100ms SLA unverified (AUDIT-PERF-001) | MEDIUM | UI-08 export timeout | DB Lead to pre-index project_id + event_timestamp before DB-INIT-001 | DB Lead |
| Lane 1 schema silent creation failure during Block 5 | MEDIUM | Critical tables missing; engine cannot run | Atomic transaction wrapper + post-build validation script (57 table count, FK check) | Block 5 Agent |

7. Next-Day Action List by Owner

### IMMEDIATE — Required Before EOD 2026-04-27

DB Lead — Execute DB-INIT-001 initialization script TODAY. Pre-index audit_event_log on project_id + event_timestamp before execution.

Parser Lead — Confirm ODA File Converter installation status on all developer machines. Document path for CADParser configuration. Close R-PARSER-01.

### 2026-04-29 — Critical Path

| Owner | Action | Blocker Closed |
| --- | --- | --- |
| Chief Architect | Deliver frozen WS event schema (gate_status_update, approval_queue_update, pipeline_progress) with field definitions + envelope structure | B-UI-01 / B-PARSER-01 |
| Chief Architect | Deliver UI-Engine Event Binding Contract (signed) — formally close B-UI-01 | B-UI-01 |
| Chief Architect | Sign off conflict_resolver.py (C9) design — formally close B-PARSER-01 | B-PARSER-01 |
| Chief Architect | Schedule CCB weekly standing meeting (recurring invite) | — |
| Program Manager | Establish CCB emergency convene procedure (contact list, decision threshold, record format) | — |
| UI Lead + QA | Run APPROVAL-WORKFLOW-001 + AUDIT-WRITE-001 integration tests (Block 2 exit criteria) | — |
| Lane 2 Block 6 Agent | Begin Block 6 (Conflict & Fallback Harness) once B-PARSER-01 cleared | — |

8. Integration Hold Status

| Hold Condition | Status at Start of Day | Status at EOD | Path to Closure |
| --- | --- | --- | --- |
| IV-2.0.0 Freeze | OPEN | OPEN — 2 baseline deviations confirmed (contract missing, WS schema absent) | Chief Architect to deliver frozen schema + signed binding contract by 2026-04-29 |
| BJ-010 Completion | OPEN | OPEN — 6 alignment points scoped but diff verification not yet performed | DB Lead to complete BJ-010 table/field diff by 2026-04-28; Lane 3 Block 6 to finalize benchmark scope |
| CCB Confirmation | OPEN — OVERDUE | OPEN — 3/8 seats unfilled, 2 days past target date. Escalating to BLOCKER. | Program Manager to call emergency CCB session EOD 2026-04-27; all 3 seats named and accepted |

Integration hold verdict: UNCHANGED. All three hold conditions (IV-2.0.0, BJ-010, CCB) remain formally open at end of day. No benchmark execution may begin. Full integration remains prohibited. The hold has not materially progressed today, though gap analysis and preparation work in Lane 3 has improved closure readiness. Path to AMBER requires all 3 blockers showing confirmed unblock progress by EOD 2026-04-28.

9. Final Daily Status

| Component Build Progress Lanes 1 & 2 producing strong build output. Lane 3 specification complete. All within frozen baseline. | Governance & Hold Closure 3 critical blockers. 2 baseline deviations in Lane 3. CCB overdue by 2 days. No material hold progress. | Schedule Risk DB-INIT-001 and CCB seat assignments both within 24-hour resolution window. Any slip cascades to all lanes. |
| --- | --- | --- |

FINAL DAILY STATUS: 🔴 RED

### Justification

- 3 CRITICAL blockers active (B-UI-01, B-UI-02, R-UI-01) — no Block 2 SQLite or WebSocket builds possible in Lane 3.

- 2 confirmed baseline deviations in Lane 3 (CCB overdue 2 days; IV-2.0.0 contract absent).

- Integration hold unchanged — all 3 hold conditions remain formally open.

- DB-INIT-001 not run — highest-impact single dependency across all 3 lanes.

- Lane 1 and Lane 2 component progress is strong and genuine — this is a governance / infrastructure failure, not a build failure.

Path to AMBER: All 3 blockers must show confirmed unblock progress by EOD 2026-04-28: B-UI-02 CLOSED (DB-INIT-001 PASS), R-UI-01 CLOSED (CCB fully seated), B-UI-01 schema draft published by Chief Architect.