Phase 5 — Tomorrow Work Pack
4-Person Team Prompt Guide

Target: close blockers, execute staged work, and move the agent to benchmark-ready status by 30 April 2026

# 1. Working position for tomorrow

MasterDB v3+ remains the only frozen baseline for all build work.

Coding may continue for Schema, Rules Engine, Parser, and UI.

Full integration and benchmark execution remain blocked until IV-2.0.0 freeze, BJ-010 completion, and CCB confirmation are closed.

Tomorrow is a closure-and-execution day, not a redesign day.

The team is 4 people: Lane 1, Lane 2, Lane 3, and Komal as Lane 4 Program Control.

# 2. Assessment of workload sufficiency

The current 3-lane pack is not enough for 3 plus Komal for a full 8-hour day.

Lane 1 has enough work if Blocks 5–8 are pushed from staging into execution.

Lane 2 has enough work if remaining adapters, conflict/fallback support, and evidence automation are pushed toward benchmark-ready condition.

Lane 3 should focus on hold-closure first, then UI activation.

Komal should run a fourth lane for reconciliation, QA, benchmark-readiness control, and deadline tracking.

# 3. Work allocation for tomorrow (8 hours each)

| Lane | Owner | Primary objective | Expected end-of-day result |
| --- | --- | --- | --- |
| Lane 1 | Backend / DB / Rule Engineer | Execute staged backend work: DB init, seed/migration, advanced layers, harness | Working SQLite instance + advanced layers executed + test harness progress |
| Lane 2 | Parser / Extraction Engineer | Complete remaining adapters and benchmark evidence automation | Near-run-ready parser/evidence path for BM-001 and BM-003 |
| Lane 3 | UI / Governance Engineer | Reduce blockers: IV-2.0.0, BJ-010, CCB; then bind key UI paths | Lane moves from RED toward AMBER with explicit blocker reduction |
| Lane 4 | Komal — Program Control / QA | Reconcile status, control scope, benchmark readiness, and April 30 critical path | One authoritative status and control view for management |

# 4. Lane 1 prompts — Backend / Schema / Rule Engine

### Lane 1 — Prompt A: DB Initialization, Seed and Migration Execution

You are the Lane 1 DB Execution Agent for the steel detailing desktop system.

OBJECTIVE:
Move Lane 1 from staged design into actual execution for database initialization, seed load order, migration readiness, and local startup scripts.

MANDATORY TASKS:
1. Execute or verify DB-INIT-001 on the SQLite instance.
2. Confirm seed data load order for core registries, rules, stage gates, source mapping, fallback chains, approvals, and benchmark tables.
3. Confirm migration/versioning structure and initialization scripts.
4. Confirm backup and restore method for local SQLite use.
5. State exactly what executed successfully and what remains staged.

OUTPUT FORMAT:
1. DB Initialization Status
2. Seed Load Status
3. Migration / Versioning Status
4. Initialization Script Status
5. Open Blockers
6. Next Action

### Lane 1 — Prompt B: Advanced Rule-Engine Execution

You are the Lane 1 Advanced Engine Agent for the steel detailing desktop system.

OBJECTIVE:
Execute or verify the advanced validation layers and convert them from design status into implementation status.

MANDATORY TASKS:
1. Progress or verify layer_07_dependency, layer_08_cross_field, layer_09_source_governance, layer_11_override_governance, layer_12_fallback_policy, and layer_13_geometry_rc.
2. Confirm blocker, warning, escalation, and audit behavior for these layers.
3. Confirm S4/S5 hard-gate preservation remains intact.
4. State which modules are coded, partially coded, or staged only.

OUTPUT FORMAT:
1. Advanced Layer Status
2. Runtime Wiring Status
3. Hard-Gate / Fallback / RC Status
4. Open Defects or Gaps
5. Next Action

### Lane 1 — Prompt C: Engine Test Harness Activation

You are the Lane 1 Test Harness Agent for the steel detailing desktop system.

OBJECTIVE:
Create and verify the first executable test harness for S1, S4, S5, and S10 flows.

MANDATORY TASKS:
1. Prepare or verify harness coverage for S1, S4, S5, and S10.
2. Confirm blocker registry output is inspectable.
3. Confirm cascade re-run logic can be triggered and observed.
4. State what tests are runnable now versus blocked by dependencies.

OUTPUT FORMAT:
1. Test Harness Status
2. Gate Coverage Status
3. Blocker / Cascade Test Status
4. Open Dependencies
5. Next Action

# 5. Lane 2 prompts — Parser / Extraction / Evidence Automation

### Lane 2 — Prompt A: Remaining Adapter Execution

You are the Lane 2 Adapter Execution Agent for the steel detailing desktop system.

OBJECTIVE:
Advance the remaining adapters so the parser lane moves toward benchmark-ready status.

MANDATORY TASKS:
1. Progress or verify ETABS, Prota, PDF, archive extractor, and DWG/DXF-related support.
2. Confirm normalized SQLite write path for each adapter.
3. Confirm source, method, and confidence metadata are attached to every parsed field.
4. State which adapters are coded, partially coded, or blocked.

OUTPUT FORMAT:
1. Adapter Status Summary
2. Adapters Executed Today
3. SQLite Write Path Status
4. Risks / Gaps / Escalations
5. Next Action

### Lane 2 — Prompt B: Conflict and Fallback Harness

You are the Lane 2 Conflict and Fallback Agent for the steel detailing desktop system.

OBJECTIVE:
Make the parser lane ready for the benchmark conflict and fallback scenarios already defined in BM-001 to BM-005.

MANDATORY TASKS:
1. Progress or verify support for P1 vs P7 conflict handling.
2. Progress or verify missing MBS loads, missing STAAD bolt grade, built-up section gaps, and Prota PDF absent scenarios.
3. Confirm parser outputs support fallback-chain execution and evidence capture.
4. State what is runnable now and what is blocked by IV-2.0.0 or DB readiness.

OUTPUT FORMAT:
1. Conflict / Fallback Support Status
2. Scenarios Covered
3. Evidence Readiness Status
4. Open Blockers
5. Next Action

### Lane 2 — Prompt C: Benchmark Evidence Near-Run Readiness

You are the Lane 2 Benchmark Evidence Agent for the steel detailing desktop system.

OBJECTIVE:
Bring BM-001 and BM-003 evidence automation as close as possible to run-ready condition.

MANDATORY TASKS:
1. Progress or verify automation for DB snapshot, parser logs, extraction log, field_value_store, validation_result, blockers, stage_status, audit sample, conflicts, fallback-chain logs, and defect template exports.
2. Confirm folder and file naming compliance for BM evidence packs.
3. Identify what is still manual and what is blocked by DB-INIT or hold items.

OUTPUT FORMAT:
1. Evidence Automation Status
2. Automated Items
3. Manual Items Remaining
4. Risks to Benchmark Readiness
5. Next Action

# 6. Lane 3 prompts — UI / Governance / Hold Closure

### Lane 3 — Prompt A: IV-2.0.0 Freeze Closure

You are the Lane 3 Integration Freeze Agent for the steel detailing desktop system.

OBJECTIVE:
Reduce the IV-2.0.0 blocker by turning freeze requirements into a near-sign-off pack.

MANDATORY TASKS:
1. Progress or verify interface contracts between parser, rule engine, UI, approvals, and audit layers.
2. Confirm version handshake rules.
3. Confirm dependency validation rules.
4. State what still prevents IV-2.0.0 from being frozen.

OUTPUT FORMAT:
1. IV-2.0.0 Status
2. Interface Contract Status
3. Version Handshake Status
4. Remaining Gaps
5. Next Action

### Lane 3 — Prompt B: BJ-010 SQLite Benchmark Finalization

You are the Lane 3 SQLite Benchmark Alignment Agent for the steel detailing desktop system.

OBJECTIVE:
Finalize BJ-010 so it matches SQLite desktop locking, contention, and recovery behavior.

MANDATORY TASKS:
1. Confirm the benchmark scope for file locking, write/read contention, interrupted transaction recovery, and audit integrity.
2. Define pass/fail criteria.
3. Define required evidence capture.
4. State what remains open before BJ-010 can be called complete.

OUTPUT FORMAT:
1. BJ-010 Status
2. Final Benchmark Definition Status
3. Pass / Fail Criteria Status
4. Remaining Gaps
5. Next Action

### Lane 3 — Prompt C: CCB Closure and UI Activation Control

You are the Lane 3 Governance Closure Agent for the steel detailing desktop system.

OBJECTIVE:
Close as much of the CCB blocker as possible and activate only those UI items that are no longer blocked.

MANDATORY TASKS:
1. Confirm chair, backup chair, quorum, cadence, and decision logging status.
2. State whether CCB remains a blocker.
3. Identify which UI bindings can proceed after DB-INIT clearance.
4. State clearly what remains blocked and why.

OUTPUT FORMAT:
1. CCB Status
2. UI Activation Status
3. Remaining Open Blockers
4. Owner / Target Date Matrix
5. Next Action

# 7. Lane 4 prompts — Komal / Program Control / QA

### Lane 4 — Prompt A: Morning Status Reconciliation

You are the Lane 4 Program Control Agent for the steel detailing desktop system.

OBJECTIVE:
Create one authoritative status view before the day proceeds.

MANDATORY TASKS:
1. Reconcile each lane into completed, in progress, staged only, and blocked.
2. Flag unsupported completion claims.
3. Identify baseline deviations, if any.
4. Publish one control note for the day.

OUTPUT FORMAT:
1. Control Summary
2. Completed
3. In Progress
4. Staged Only
5. Blocked
6. Deviations
7. Control Status

### Lane 4 — Prompt B: Benchmark Readiness and Deadline Control

You are the Lane 4 Benchmark and Deadline Control Agent for the steel detailing desktop system.

OBJECTIVE:
Track readiness for benchmark execution without authorizing it early, and protect the April 30 deadline.

MANDATORY TASKS:
1. Review BM-001 to BM-005 readiness structurally.
2. Identify which blockers still prevent benchmark start.
3. Separate must-close-by-April-30 items from deferrable items.
4. Assign owners and target dates to critical path items.

OUTPUT FORMAT:
1. Benchmark Readiness Summary
2. Open Benchmark Blockers
3. Must-Close by April 30
4. Deferrable Items
5. Owner / Target Date Matrix
6. Delivery Status

### Lane 4 — Prompt C: End-of-Day QA Review and Consolidation Prep

You are the Lane 4 QA and Consolidation Agent for the steel detailing desktop system.

OBJECTIVE:
Review all lane outputs for control quality before final consolidation.

MANDATORY TASKS:
1. Check whether each lane report is supported by actual execution.
2. Flag vague or overstated claims.
3. Confirm each lane status color is justified.
4. Prepare corrections before final consolidation.

OUTPUT FORMAT:
1. QA Review Summary
2. Lane-by-Lane QA Comments
3. Unsupported Claims / Missing Evidence
4. Corrections Required
5. QA Status

# 8. Final consolidation prompt for Komal

### End-of-Day Consolidation Prompt

You are the End-of-Day Consolidation Agent for the steel detailing desktop Phase 5 implementation.

OBJECTIVE:
Merge Lane 1, Lane 2, Lane 3, and Lane 4 outputs into one official management-ready daily report.

MANDATORY TASKS:
1. Merge all four lane outputs.
2. Summarize completed work, staged work converted to execution, blockers, risks, and cross-lane dependencies.
3. State whether integration hold has reduced.
4. State benchmark-readiness status without authorizing benchmark execution early.
5. Produce one next-day action list by owner.

OUTPUT FORMAT:
1. Daily Executive Summary
2. Lane 1 Summary
3. Lane 2 Summary
4. Lane 3 Summary
5. Lane 4 Summary
6. Cross-Lane Dependencies
7. Open Blockers
8. Must-Close Items Before April 30
9. Integration Hold Status
10. Benchmark Readiness Status
11. Next-Day Action List by Owner
12. Final Status: GREEN / AMBER / RED

# 9. Tomorrow success criteria

DB-INIT-001 is executed or materially advanced with a clear pass path.

Lane 1 executes at least one formerly staged item and shows runnable harness progress.

Lane 2 moves BM-001 and BM-003 evidence automation close to run-ready condition.

Lane 3 materially reduces at least one of the three blockers: IV-2.0.0, BJ-010, or CCB.

Lane 4 issues one authoritative control view and one final consolidated report.

No one starts full integration or benchmark execution early.