## 0. Reconciliation Authority
BASELINE RECONCILIATION AUTHORITY PACK — IFS-MASTERDB-V3-FINAL ¦ Phase 5 ¦ April 23, 2026
One authoritative document reconciling MasterDB v3+ architectural counts against active implementation scope. IT, QA, and Management must use these numbers — not the architectural document directly.
SECTION 1 — FINAL AUTHORITATIVE COUNTS (Single source of truth for implementation)
Category | MasterDB v3+ Architectural Figure | Architectural Breakdown | Active Implementation Count | Deferred / Not-Built Count | Deprecated Count | Final Build Number | Variance from Architecture | Variance Explanation
PRIMARY MODULES (DB Tables) | 58 primary modules | M-01 to M-58 ¦ L1(3) + L2(12) + L3(5) + L4(7) + L5(4) + L6(2) + L7(4) + L8(3) + L9(4) + L10(10) + M-39 cross-layer(1) + M-40 to M-44 gap(5) | 54 active modules | 4 deferred (M-36, M-37, M-38 Register tables + M-58 extension) | 0 deprecated | 54 active ¦ 4 deferred | −4 vs architecture | M-36/M-37/M-38 are register/readiness tables (admin records, not engineering DB tables). M-58 is an EXTENSION of M-30 — rows merge into M-30 trigger table; not a separate physical table. Architecture count of 58 is correct for design. Build count is 54 physical PostgreSQL tables + 4 admin/merged items.
SUB-REGISTRIES | 12 sub-registries | SR-001 to SR-009 (section routes) ¦ TH-B01–B10, TH-O01–O08, TH-I01–I05 (thresholds) ¦ IDX-001–IDX-024 (indexes) | 3 sub-registry tables: section_standard_route (9 rows), threshold_master (23 rows), indexing_strategy_master (24 rows) | 0 deferred | 0 deprecated | 3 physical tables (56 total rows) | Architecture says 12; active is 3 tables | MISMATCH EXPLANATION: Architecture counted individual sub-registry ROWS (9 SR + 23 TH + 24 IDX = 56 rows) as if each were a registry, but they are actually 3 physical tables. Final authoritative figure: 3 sub-registry PostgreSQL tables with 56 total rows.
FIELDS (Field Dictionary) | 196 fields | F-001 to F-156 (original 156) + F-157 to F-196 (40 gap-remediation fields added in v2) | 196 fields — all active | 0 deferred | 0 deprecated (F-039/F-040 cardinality updated, not deprecated — fields retained as display aggregates) | 196 fields | 0 — exact match | All 196 fields are active. F-039 and F-040 were upgraded from single-value to ordered-list (via M-41 bay_geometry_master) but remain in the field dictionary as display aggregates. No field has been removed.
VALIDATION RULES (Rules Sheet) | 293 rules (Rules sheet header) | 133 Validation + 28 Cross-Field + 16 Source-Governance + 22 Stage-Gate + 72 Override + 22 Fallback-Policy = 293 | 293 rules — all active | 0 deferred | 0 deprecated | 293 rules | 0 — exact match | All 293 rules are active. Note: Phase 4 document (PROMPT_4) stated 271 rules. The updated count of 293 in the Rules sheet reflects 22 additional Fallback-Policy rules integrated from M-22 fallback_rule_master in v3. 293 is the authoritative implementation figure.
STAGE GATES | 10 stage gates (S1–S10) | S1 Intake ¦ S2 Template ¦ S3 Field Population ¦ S4 AB Output ¦ S5 GA Output ¦ S6 Sheeting ¦ S7 Shop ¦ S8 Shipping ¦ S9 Installation ¦ S10 Release | 10 stage gates — all active | 0 deferred | 0 deprecated | 10 stage gates | 0 — exact match | All 10 gates are active. S4 (AB) and S5 (GA) remain hard gates. No gate has been merged or removed.
SUPERVISORY VALIDATION LAYERS + GATES | 4 validation layers (L1–L4) + 4 supervisory gates (G1–G4) | L1 Source Validation ¦ L2 DB Validation ¦ L3 Geometry Reconciliation ¦ L4 Release Validation ¦ G1–G4 gate decisions per layer | 4 layers + 4 gates — all active | 0 deferred | 0 deprecated | 4 layers + 4 gates | 0 — exact match | Defined in M-54 supervisory_validation_master. These are validation architecture layers — distinct from the 10 stage gates above. Both sets are active.
GEOMETRY RECONCILIATION RULES | 22 RC rules + 14 tolerance rules + 3 severity levels | RC-001 to RC-022 ¦ TOL-001 to TOL-014 ¦ SEV-1/SEV-2/SEV-3 | 22 RC + 14 TOL + 3 SEV — all active | 0 deferred | 0 deprecated | 22 RC + 14 TOL + 3 SEV | 0 — exact match | Defined in M-45 to M-48. All geometry reconciliation rules are active from Day 1 of DXF generation.
CONTROLLED VOCABULARIES (Enumerations) | 22 code lists | CV-01 to CV-22 covering all field enumerations in controlled_value_master (M-39) | 22 code lists — all active | 0 deferred | 0 deprecated | 22 code lists | 0 — exact match | All 22 controlled vocabularies are active. Note: Gap 6 (design standard) proposed CV-23 for standard-specific material grades. CV-23 is PENDING — added as open mismatch item below.
DESIGN STANDARD BRANCHES | 4 standard branches (DS-001 to DS-004) | IS-Indian ¦ AISC-US ¦ BS-UK ¦ Eurocode-EU ¦ Defined in M-49 | 4 branches — all active | 0 deferred | 0 deprecated | 4 design standard branches | 0 — exact match | All 4 branches active. F-191 (project_design_standard) is mandatory at Stage S1. All downstream field lookups branch on this field.
SECTION ROUTING PATHS | 9 routes (SR-001 to SR-009) | SR-001 to SR-008: Rolled/BuiltUp × 4 standards ¦ SR-009: NonStandard escalation | 9 routes — all active | 0 deferred | 0 deprecated | 9 routes | 0 — exact match | All 9 routes active. SR-009 (NonStandard) triggers M-51 nonstandard_section_review_master. Critical: SR-009 BLOCKS weight calculation and BOQ generation until dual DE+PM approval.
POSTGRESQL TABLES (Total Physical) | Not stated as single number in architecture | 58 primary modules + 3 sub-registry tables = 61 physical tables | 54 active modules + 3 sub-registry tables = 57 active PostgreSQL tables | 4 deferred (admin/merged items) | 0 deprecated | 57 physical PostgreSQL tables | MISMATCH — architecture did not state a total table count | The architecture listed modules, not PostgreSQL tables. This reconciliation declares 57 physical PostgreSQL tables as the authoritative implementation build target. The 4 deferred items (M-36/37/38/58) are either admin registers or merged into other tables.
MANUAL REVIEW TRIGGERS | 18 triggers (M-30) + 7 extension triggers (M-58) = 25 total | T-001 to T-018 in M-30 ¦ T-019 to T-025 in M-58 extension | 25 triggers — T-001 to T-025, all in one physical table | 0 deferred | 0 deprecated | 25 manual review triggers | Architecture split across 2 modules; implementation merges into 1 table | M-58 is an EXTENSION of M-30 — not a separate physical table. Both sets of triggers (T-001 to T-025) are stored in manual_review_trigger_master. Final build: 1 table, 25 rows.
OVERRIDE STATUSES | 7 override statuses | override-prohibited ¦ override-not-applicable ¦ override-allowed-with-review ¦ override-allowed-with-approval ¦ override-allowed-for-presentation-only ¦ override-allowed-for-metadata-only ¦ override-allowed-for-sequence-control-only | 7 statuses — all active | 0 deferred | 0 deprecated | 7 override statuses | 0 — exact match | All 7 override statuses active. 28 fields carry override-prohibited status — these cannot be overridden by any mechanism, including gate bypass.
RELEASE TYPES | 5 release types (RA-001 to RA-005) | Standard ¦ Minor-Open ¦ Emergency ¦ Phased ¦ Seismic | 5 release types — all active | 0 deferred | 0 deprecated | 5 release types | 0 — exact match | Defined in M-56. RA-003 Emergency requires DE co-sign. RA-005 Seismic requires external peer reviewer before S10.
MULTI-ROLE APPROVAL CASES | 8 multi-role approval cases (MA-001 to MA-008) | Defined in M-55 approval_role_matrix | 8 cases — all active | 0 deferred | 0 deprecated | 8 approval cases | 0 — exact match | Subject to CR-001 (role model confirmation). Cases are structurally defined; role names require org chart confirmation before coding.
THRESHOLD CLASSIFICATIONS | 23 thresholds (TH-B01–B10 + TH-O01–O08 + TH-I01–I05) | 10 Blocking + 8 Operational + 5 Informational = 23 total | 23 thresholds — all active | 0 deferred | 0 deprecated | 23 thresholds | 0 — exact match | All thresholds defined. Each threshold has exactly one type (no conflicts). Blocking thresholds tied to release gate logic.
PERFORMANCE INDEXES | 24 justified indexes (IDX-001 to IDX-024) | Covering 12 critical tables. Composite keys for multi-column lookups. | 24 indexes — all active | 0 deferred | 0 deprecated | 24 PostgreSQL indexes | 0 — exact match | All indexes are justified — no generic indexes included. Composite keys defined for multi-column lookups.
OUTPUT CLASSES | 6 output classes | AB (Anchor Bolt) ¦ GA (General Arrangement) ¦ Sheeting ¦ Shop/Detail ¦ Shipping ¦ Installation | 6 output classes — all active | 0 deferred | 0 deprecated | 6 output classes | 0 — exact match | All 6 output classes active. AB and GA have hard gate dependency. Phase 3 outputs (Sheeting, Shop, Shipping, Installation) require AB+GA gates to pass.
SECTION 2 — ARCHITECTURAL vs ACTIVE IMPLEMENTATION MAPPING (Module-by-Module Classification)
Module ID | Module Name | Layer | Domain | Architectural Status | Implementation Classification | Physical Table Name | Build Priority | Blocked By | Notes
M-01 | intake_job_registry | L1 | Historical Intake | Architectural | ACTIVE — Phase 1 DB | intake_job_registry | Phase 1 | BUILD-04 | 22 jobs parsed; 50 target
M-02 | intake_sheet_registry | L1 | Historical Intake | Architectural | ACTIVE — Phase 1 DB | intake_sheet_registry | Phase 1 | BUILD-04 | 3665+ sheets
M-03 | historical_reference_registry | L1 | Historical Intake | Architectural | ACTIVE — Phase 1 DB | historical_reference_registry | Phase 1 | BUILD-04 | Pattern reference only
M-04 | template_family_master | L2 | Template & Presentation | Architectural | ACTIVE | template_family_master | Phase 1 | BUILD-04 | 15+ families; 8 Standard
M-05 | template_variant_master | L2 | Template & Presentation | Architectural | ACTIVE | template_variant_master | Phase 1 | BUILD-04
M-06 | title_block_master | L2 | Template & Presentation | Architectural | ACTIVE | title_block_master | Phase 1 | BUILD-04
M-07 | revision_block_master | L2 | Template & Presentation | Architectural | ACTIVE | revision_block_master | Phase 1 | BUILD-04
M-08 | note_block_master | L2 | Template & Presentation | Architectural | ACTIVE | note_block_master | Phase 1 | BUILD-04
M-09 | legend_block_master | L2 | Template & Presentation | Architectural | ACTIVE | legend_block_master | Phase 1 | BUILD-04
M-10 | symbol_family_master | L2 | Template & Presentation | Architectural | ACTIVE | symbol_family_master | Phase 1 | BUILD-04
M-11 | layout_rule_master | L2 | Template & Presentation | Architectural | ACTIVE | layout_rule_master | Phase 1 | BUILD-04
M-12 | table_family_master | L2 | Template & Presentation | Architectural | ACTIVE | table_family_master | Phase 1 | BUILD-04
M-13 | callout_rule_master | L2 | Template & Presentation | Architectural | ACTIVE | callout_rule_master | Phase 1 | BUILD-04 | CR-004 open: mark overflow
M-14 | sequencing_rule_master | L2 | Template & Presentation | Architectural | ACTIVE | sequencing_rule_master | Phase 1 | BUILD-04
M-15 | naming_rule_master | L2 | Template & Presentation | Architectural | ACTIVE | naming_rule_master | Phase 1 | BUILD-04
M-16 | field_dictionary_master | L3 | Field Semantics | Architectural | ACTIVE — CORE | field_dictionary_master | Phase 1 | BUILD-04 | 196 fields; primary reference
M-17 | field_alias_master | L3 | Field Semantics | Architectural | ACTIVE | field_alias_master | Phase 1 | BUILD-04
M-18 | field_entity_scope_map | L3 | Field Semantics | Architectural | ACTIVE | field_entity_scope_map | Phase 1 | BUILD-04
M-19 | field_output_impact_map | L3 | Field Semantics | Architectural | ACTIVE | field_output_impact_map | Phase 1 | BUILD-04
M-39 | controlled_value_master | L3 | Field Semantics | Architectural | ACTIVE | controlled_value_master | Phase 1 | BUILD-04 | 22 CVs; CV-23 pending
M-41 | bay_geometry_master | L3 | Multi-Span Geometry | Architectural (v2 gap) | ACTIVE — CRITICAL | bay_geometry_master | Phase 1 | BUILD-04 | Ordered-list cardinality fix
M-42 | crane_system_master | L3 | Crane Engineering | Architectural (v2 gap) | ACTIVE | crane_system_master | Phase 1 | BUILD-04 | Conditional on F-060=CraneBay
M-20 | field_source_map | L4 | Source Mapping | Architectural | ACTIVE | field_source_map | Phase 1 | BUILD-04 | 8 priority levels
M-21 | transformation_rule_master | L4 | Source Mapping | Architectural | ACTIVE | transformation_rule_master | Phase 1 | BUILD-04
M-22 | fallback_rule_master | L4 | Source Mapping | Architectural | ACTIVE | fallback_rule_master | Phase 1 | BUILD-04
M-23 | null_policy_master | L4 | Source Mapping | Architectural | ACTIVE | null_policy_master | Phase 1 | BUILD-04
M-24 | conflict_rule_master | L4 | Source Mapping | Architectural | ACTIVE | conflict_rule_master | Phase 1 | BUILD-04
M-25 | field_dependency_map | L4 | Source Mapping | Architectural | ACTIVE | field_dependency_map | Phase 1 | BUILD-04 | 31 derived fields
M-40 | connection_detail_master | L4 | Connection Engineering | Architectural (v2 gap) | ACTIVE | connection_detail_master | Phase 2 | BUILD-07/11 | Gap 1 resolved
M-43 | buildup_section_master | L4 | Fabricated Section | Architectural (v2 gap) | ACTIVE | buildup_section_master | Phase 1 | BUILD-04 | Gap 7 resolved; PEB primary
M-26 | validation_rule_master | L5 | Validation & Override | Architectural | ACTIVE — CORE | validation_rule_master | Phase 1 | BUILD-04 | 293 rules (not 271 — see Sect 3)
M-27 | validation_rule_field_map | L5 | Validation & Override | Architectural | ACTIVE | validation_rule_field_map | Phase 1 | BUILD-04 | Junction table
M-28 | override_rule_master | L5 | Validation & Override | Architectural | ACTIVE | override_rule_master | Phase 1 | BUILD-04 | 42 matrices; 28 prohibited fields
M-29 | override_role_matrix | L5 | Validation & Override | Architectural | ACTIVE — pending CR-001 | override_role_matrix | Phase 1 | BUILD-04 + CR-001 | Role model pending
M-30 | manual_review_trigger_master | L5 | Validation & Override | Architectural | ACTIVE — merged with M-58 | manual_review_trigger_master | Phase 2 | BUILD-05 | 25 triggers (T-001 to T-025)
M-31 | audit_log_requirement_master | L6 | Audit & Traceability | Architectural | ACTIVE | audit_log_requirement_master | Phase 1 | BUILD-04 | 10 mandatory attrs per event
M-32 | traceability_path_master | L6 | Audit & Traceability | Architectural | ACTIVE | traceability_path_master | Phase 1 | BUILD-04
M-33 | output_stage_gate_master | L7 | Stage Gate Control | Architectural | ACTIVE — CORE | output_stage_gate_master | Phase 1 | BUILD-04 | 10 gates; S4 and S5 are hard gates
M-34 | stage_dependency_master | L7 | Stage Gate Control | Architectural | ACTIVE | stage_dependency_master | Phase 1 | BUILD-04 | Re-run cascade rules
M-35 | release_blocker_master | L7 | Stage Gate Control | Architectural | ACTIVE | release_blocker_master | Phase 1 | BUILD-04
M-44 | p305_supervisor_logic_master | L7 | P3-05 Supervisor | Architectural (v2 gap) | ACTIVE | p305_supervisor_logic_master | Phase 3 | BUILD-14 | Gap 4 resolved
M-36 | unresolved_issue_register | L8 | Review & Future | Architectural | DEFERRED — Admin register | unresolved_issue_register | Admin | N/A | Not a system-runtime table; managed in Phase 5 Control Pack
M-37 | implementation_assumption_register | L8 | Review & Future | Architectural | DEFERRED — Admin register | implementation_assumption_register | Admin | N/A | Not a system-runtime table
M-38 | phase2_readiness_register | L8 | Review & Future | Architectural | DEFERRED — Admin register | phase2_readiness_register | Admin | N/A | Managed in Phase 5 Control Pack
M-45 | geometry_reconciliation_master | L9 | Geometry Reconciliation | Architectural | ACTIVE | geometry_reconciliation_master | Phase 2 | BUILD-07/08 | 22 RC rules
M-46 | geometry_check_result_log | L9 | Geometry Reconciliation | Architectural | ACTIVE — Immutable log | geometry_check_result_log | Phase 2 | BUILD-07/08 | 18-col schema; no delete
M-47 | geometry_tolerance_master | L9 | Geometry Reconciliation | Architectural | ACTIVE | geometry_tolerance_master | Phase 1 | BUILD-04 | 14 TOL rules
M-48 | geometry_conflict_action_master | L9 | Geometry Reconciliation | Architectural | ACTIVE | geometry_conflict_action_master | Phase 1 | BUILD-04 | 3 severity levels
M-49 | project_design_standard_master | L10 | Engineering Standardization | Architectural | ACTIVE | project_design_standard_master | Phase 1 | BUILD-04 | 4 standard branches
M-50 | section_standard_route_master | L10 | Engineering Standardization | Architectural | ACTIVE | section_standard_route_master | Phase 1 | BUILD-04 | 9 routes SR-001 to SR-009
M-51 | nonstandard_section_review_master | L10 | Engineering Standardization | Architectural | ACTIVE | nonstandard_section_review_master | Phase 2 | BUILD-05 | Dual DE+PM approval
M-52 | material_grade_mapping_master | L10 | Engineering Standardization | Architectural | ACTIVE | material_grade_mapping_master | Phase 1 | BUILD-04 | 8 mappings MM-001 to MM-008
M-53 | seismic_standard_mapping_master | L10 | Engineering Standardization | Architectural | ACTIVE | seismic_standard_mapping_master | Phase 1 | BUILD-04 | CR-005 open: seismic standard
M-54 | supervisory_validation_master | L10 | Supervisory Governance | Architectural | ACTIVE | supervisory_validation_master | Phase 1 | BUILD-04 | 4 layers + 4 supervisory gates
M-55 | approval_role_matrix | L10 | Supervisory Governance | Architectural | ACTIVE — pending CR-001 | approval_role_matrix | Phase 1 | BUILD-04 + CR-001 | 8 MA cases; role model pending
M-56 | release_authority_master | L10 | Supervisory Governance | Architectural | ACTIVE — pending CR-003 | release_authority_master | Phase 1 | BUILD-04 + CR-003 | 5 release types
M-57 | gate_bypass_control_master | L10 | Supervisory Governance | Architectural | ACTIVE | gate_bypass_control_master | Phase 1 | BUILD-04 | 4 bypass types BP-001 to BP-004
M-58 | manual_review_trigger_master (EXTENSION) | L10 | Supervisory Governance | Architectural | MERGED into M-30 — no separate table | → merged into manual_review_trigger_master | Phase 2 | BUILD-05 (merged) | T-019 to T-025 rows added to M-30 table
SR-REG | section_standard_route (sub-registry rows) | L10 | Sub-Registry | Architectural | ACTIVE — 9 rows in M-50 table | section_standard_route_master (9 rows) | Phase 1 | BUILD-04 | SR-001 to SR-009
TH-REG | threshold_master (sub-registry) | GH Patch | Sub-Registry | Architectural (v4 patch) | ACTIVE — standalone table | threshold_master | Phase 1 | BUILD-01 | 23 rows: 10B+8O+5I
IDX-REG | indexing_strategy_master (sub-registry) | GH Patch | Sub-Registry | Architectural (v4 patch) | ACTIVE — standalone table | indexing_strategy_master | Phase 1 | BUILD-01 | 24 justified indexes
SW-REG | software_source_mapping_matrix (sub-registry) | GH Patch | Sub-Registry | Architectural (v4 patch) | ACTIVE — standalone table | software_source_mapping_matrix | Phase 1 | BUILD-04 | 36 rows × 4 software
SECTION 3 — RULE COUNT RECONCILIATION (271 in Phase 4 doc vs 293 in MasterDB Rules Sheet)
VARIANCE EXPLANATION: The Phase 4 specification document (PROMPT_4_OUTPUT) stated 271 rules. The MasterDB v3+ Rules sheet states 293 rules. This is NOT a conflict — it is an additive update. The 22 additional rules are Fallback-Policy rules (from M-22 fallback_rule_master) formally integrated into the master rule register during v3 consolidation. The authoritative implementation figure is 293 rules. Phase 4 document is superseded by MasterDB v3+ for implementation purposes.
Rule Category | Phase 4 Doc Count | MasterDB v3+ Count | Difference | Explanation
Validation Rules (VR) | 133 | 133 | 0 | Exact match. R-001 to R-133.
Cross-Field Rules (XF) | 28 | 28 (formally: 28 XF + additional XF-NEW) | 0 declared | MasterDB carries original 28 XF plus XF-NEW rules from gap remediation. Gap XF rules integrated into validation_rule_master.
Source Governance Rules (SG) | 16 | 16 | 0 | Exact match. SG-001 to SG-016.
Stage Gate Rules | 22 | 22 | 0 | Exact match. 10 stage gates × gate pass/fail/bypass rules.
Override Governance Rules | 72 | 72 | 0 | Exact match. 42 override matrices × applicable fields.
Fallback Policy Rules | NOT COUNTED | 22 | +22 | Phase 4 did not include fallback rules in the rule count. MasterDB v3+ formally integrated 22 fallback policy rules from M-22 fallback_rule_master into the master rule register.
TOTAL | 271 (as stated in Phase 4) | 293 (authoritative) | +22 | 293 is the final authoritative implementation count. IT must build against 293 rules.
SECTION 4 — DEFERRED / DEPRECATED / MERGED REGISTER
Item ID | Item Name | Classification | Reason | Impact on Build | Resolution Path
M-36 | unresolved_issue_register | DEFERRED — Admin Register | This is an administrative tracking register for unresolved governance items, not a system-runtime PostgreSQL table. It does not contain engineering data, field values, or rules. | Zero impact on agent pipeline. The 12 unresolved items are tracked in the Phase 5 Control Pack (Change Control Register). No agent reads from this table at runtime. | Remains as an administrative document table if desired. Can be implemented as a simple log file or admin spreadsheet. NOT required before Phase 2 coding begins.
M-37 | implementation_assumption_register | DEFERRED — Admin Register | Administrative register of implementation assumptions requiring confirmation. Not used by any agent at runtime. | Zero impact on agent pipeline. Assumptions tracked in Phase 5 Control Pack Build Readiness Checklist. | Can be implemented as a simple admin record table. NOT required before Phase 2 coding begins.
M-38 | phase2_readiness_register | DEFERRED — Admin Register | Administrative readiness checklist. Not a system-runtime table. Content managed in Phase 5 Control Pack. | Zero impact on agent pipeline. Readiness tracked in Phase 5 Control Pack Sheet 7. | Can be implemented as a simple admin record table. NOT required before Phase 2 coding begins.
M-58 | manual_review_trigger_master (extension) | MERGED into M-30 | M-58 is explicitly defined in MasterDB as an EXTENSION of M-30 — it adds rows T-019 to T-025 to the same trigger table. Implementing it as a separate table would create a join dependency where none is needed. | Build ONE table: manual_review_trigger_master with 25 rows (T-001 to T-025). M-58 rows are appended rows in the same table, not a separate join. | IT to load all 25 trigger rows (T-001 to T-018 from M-30 + T-019 to T-025 from M-58) into a single manual_review_trigger_master table. No separate table required.
CV-23 | Controlled Vocabulary 23 (proposed) | PENDING — Not yet created | Gap 6 (design standards) proposed adding CV-23 for standard-specific material grades (IS/AISC/BS/EC cross-references). This was not formally added to controlled_value_master in v3. | M-52 material_grade_mapping_master (8 rows MM-001 to MM-008) covers cross-standard mapping. CV-23 may be redundant or may be needed as an enumeration extension. | Engineering decision required: Does CV-23 add value beyond M-52? If yes, add as CV-23 via CR process. If M-52 is sufficient, close as not-required. Logged as OPEN MISMATCH #3 below.
GH-C07 / SC-004 / SC-005 | MBS-specific fallback rule names | PENDING RENAME | Fallback rules SC-004 and SC-005 reference 'MBS XML' in their names, implying only MBS has load/section gaps. Other software (STAAD, ETABS) may have same gaps. | Low impact — naming issue only. Rules themselves are correct. Risk: IT might implement MBS-only check when all software should be checked. | Rename SC-004 → 'P1 Source — Loads Missing (all software)'. Rename SC-005 → 'P1 Source — Section Properties Incomplete (all software)'. Add equivalent checks for STAAD/ETABS/Prota. Log as CR.
GH-C08 / P-015/P-018/P-020 | Template patterns with MBS-specific labels | PENDING NOTE UPDATE | Template Patterns P-015, P-018, P-020 annotated as 'MBS jobs' in Notes column. These patterns are software-neutral presentation conventions. | Low impact — annotation issue only. Templates will apply correctly regardless of software. | Update Notes column to remove 'MBS jobs' reference → 'Standard across all reference jobs'. Low priority. Log as CR.
SECTION 5 — IMPLEMENTATION SCOPE NOTE (What IT builds, what IT does not build)
IN SCOPE — Build as PostgreSQL Tables |  | 57 physical PostgreSQL tables: 54 active primary modules + 3 sub-registry tables (threshold_master, indexing_strategy_master, software_source_mapping_matrix). All 293 rules loaded into validation_rule_master. All 196 fields loaded into field_dictionary_master. All 25 triggers loaded into manual_review_trigger_master.
IN SCOPE — Build as Application Code |  | 4 parsers (STAAD, MBS, ETABS, Prota Steel) ¦ FastAPI backend ¦ LangGraph agent orchestration ¦ React + TailwindCSS frontend ¦ WebSocket live tracking ¦ Celery + Redis task queue ¦ ezdxf DXF generation ¦ ODA DXF→DWG conversion ¦ Ollama LLM local engine ¦ 3-level learning system
IN SCOPE — Populate from Phase 1 |  | All Layer 1 tables (M-01 to M-03) from 50 reference jobs. All Layer 2 template tables (M-04 to M-15). All controlled vocabularies (CV-01 to CV-22). All source mapping tables (M-20 to M-25). Benchmark job corpus (BM-001 to BM-003).
NOT IN SCOPE — Admin Records (not PostgreSQL tables) |  | M-36 unresolved_issue_register, M-37 implementation_assumption_register, M-38 phase2_readiness_register — these are administrative registers managed in the Phase 5 Control Pack, not system-runtime database tables.
NOT IN SCOPE — Separate Table (merged) |  | M-58 manual_review_trigger_master extension — rows T-019 to T-025 are appended to the M-30 table. No separate table is built.
PENDING RESOLUTION — Cannot code until CRs resolved |  | override_role_matrix (M-29) and approval_role_matrix (M-55) — structural tables built, but role names cannot be finalized until CR-001 (role model) is resolved. release_authority_master (M-56) — 5 release types defined, but final authority role cannot be coded until CR-003 (release authority) is resolved.
PENDING RESOLUTION — Engineering decision needed |  | CV-23 (material grade enumeration extension) — pending decision on whether M-52 material_grade_mapping_master is sufficient or CV-23 is required. seismic_standard_mapping (M-53) — implementation complete, but Zone V/SDC-F/DCH external peer review requirement depends on CR-005.
SECTION 6 — OPEN MISMATCHES REQUIRING APPROVAL (Must be resolved before final build sign-off)
Mismatch ID | Category | Architectural Statement | Current Status | Variance | Resolution Required | Approval Authority | Priority
OM-001 | Module Count | MasterDB Executive Summary states '54 primary modules + 12 sub-registries'. This implies 12 is a count of individual sub-registry tables. | Actual count: 3 sub-registry tables (threshold_master, indexing_strategy_master, software_source_mapping_matrix) with 56 total rows. The number 12 appears to be a row-group count (9 SR routes + 3 table groups), not a table count. | Architecture: 12 sub-registries. Build: 3 physical tables. The number 12 is misleading. | Engineering Lead + IT Lead must formally approve: '3 physical sub-registry tables is the correct implementation target. The architectural figure of 12 sub-registries referred to row-group categories, not separate tables.' | Engineering Lead + IT Lead | HIGH — Must resolve before DB schema is finalized
OM-002 | Rule Count | Phase 4 document stated 271 rules. MasterDB v3+ Rules sheet states 293 rules. | MasterDB v3+ is the authoritative document. 22 additional Fallback-Policy rules were added during v3 consolidation. Phase 4 document is superseded. | +22 rules. Architecture document (Phase 4) is superseded by MasterDB v3+. | Engineering Lead must formally acknowledge: '293 is the authoritative rule count. Phase 4 figure of 271 is superseded. No rules have been removed or weakened — 22 fallback rules were added.' | Engineering Lead | HIGH — Must document approval before coding validation engine
OM-003 | CV-23 Status | Gap 6 solution proposed adding CV-23 as a standard-specific material grade extension to controlled_value_master. | CV-23 was NOT added to the MasterDB. M-52 material_grade_mapping_master covers cross-standard equivalency with 8 validated mappings (MM-001 to MM-008). It is unclear if CV-23 is required in addition. | CV-23 is proposed but not created. Gap between Gap 6 solution text and actual MasterDB content. | Engineering decision: Is M-52 sufficient for material grade governance, or is CV-23 required as an enumeration list? If required, raise CR to add CV-23. If M-52 sufficient, formally close CV-23 as not-required. | Design Engineer | MEDIUM — Decision before coding material grade validation
OM-004 | M-58 Physical Table | MasterDB lists M-58 as a distinct module 'manual_review_trigger_master (EXTENSION)'. | MasterDB itself states: 'Do not replace M-30. This M-58 is an EXTENSION TABLE for T-019 onwards.' This means T-019 to T-025 are rows in M-30's table, not a separate table. | Architecture lists M-58 as a separate module ID, but implementation requires merging into M-30. The physical table count is 57 (not 58). | IT Lead to confirm: 'M-58 rows will be loaded into the M-30 physical table (manual_review_trigger_master). No separate M-58 table will be created. Total physical tables: 57.' Engineering Lead to acknowledge. | IT Lead + Engineering Lead | HIGH — Must resolve before DB schema is finalized
OM-005 | Template Notes (MBS bias) | Template patterns P-015, P-018, P-020 have Notes referencing 'MBS jobs' — implying software-specific templates. | Templates are presentation-layer conventions. They are software-neutral. The MBS reference is historical annotation from when all reference jobs were MBS-based. | Template annotations imply MBS-specific applicability. Templates should be software-neutral. | Drafting Lead to confirm: 'Template patterns P-015/P-018/P-020 apply to all design software sources, not MBS only. Notes will be updated via CR.' Raise CR per GH-C08. | Drafting Lead | LOW — Does not block build. Raise CR for next maintenance cycle
FINAL AUTHORITATIVE DECLARATION — Use these numbers for all implementation planning
PRIMARY POSTGRESQL TABLES |  | 57 | 54 active modules + 3 sub-registry tables (not 58+12 as stated in architecture)
FIELDS IN FIELD DICTIONARY |  | 196 | F-001 to F-196. All active. No deprecated fields.
VALIDATION + GOVERNANCE RULES |  | 293 | Not 271 (Phase 4 figure). 22 Fallback-Policy rules added in v3 consolidation.
STAGE GATES |  | 10 | S1 to S10. S4 (AB) and S5 (GA) are hard gates.
MANUAL REVIEW TRIGGERS |  | 25 | T-001 to T-025. All in one physical table (M-30). M-58 rows merged in.
CONTROLLED VOCABULARIES |  | 22 | CV-01 to CV-22. CV-23 pending engineering decision (OM-003).
OVERRIDE-PROHIBITED FIELDS |  | 28 | Cannot be overridden by any mechanism under any circumstance.
DESIGN STANDARD BRANCHES |  | 4 | IS-Indian ¦ AISC-US ¦ BS-UK ¦ Eurocode-EU. Mandatory via F-191 at Stage S1.
GEOMETRY RECONCILIATION RULES |  | 22 RC + 14 TOL + 3 SEV | Active from Day 1 of DXF generation.
OUTPUT CLASSES |  | 6 | AB ¦ GA ¦ Sheeting ¦ Shop ¦ Shipping ¦ Installation.
OPEN MISMATCHES REQUIRING APPROVAL |  | 5 | OM-001 to OM-005. 3 HIGH priority — must resolve before DB schema finalized.
DEFERRED ITEMS (not built as tables) |  | 4 | M-36, M-37, M-38 (admin registers) + M-58 (merged into M-30).

## 1. Baseline Summary
INFINITI SOLUTIONS — STEEL DETAILING AUTOMATION
PHASE 5 — IMPLEMENTATION BASELINE FREEZE ¦ STEP 1 — BASELINE CONTROL PACK ¦ April 23, 2026
SECTION 1 — IMPLEMENTATION BASELINE SUMMARY
Baseline Name |  | MasterDB v3+ — Infiniti Solutions Steel Detailing Automation
Baseline ID |  | IFS-MASTERDB-V3-FINAL-20260423
Issued Date |  | 23-Apr-2026
Issued By |  | Phase 5 Implementation Control Agent
Based On |  | MasterDB_version3_Finalized.xlsx (Gap-Remediated, Prompt EF Patch Applied)
Architecture Version |  | v1.0 — April 2026 (README.md — Infiniti Solutions)
Phase 4 Output Version |  | PROMPT_4_OUTPUT_VALIDATION_AND_OVERRIDE_SPECIFICATION.md — April 20, 2026
Total Fields Frozen |  | 196 fields (F-001 to F-196) — 40 new fields from v2 gap remediation included
Total Validation Rules Frozen |  | 271 rules (133 validation + 28 cross-field + 16 source-governance + 22 stage-gate + 72 override)
Total Modules Frozen |  | 58 modules across 10 layers + 12 sub-registries
Output Classes Frozen |  | AB (Anchor Bolt) ¦ GA (General Arrangement) ¦ Sheeting ¦ Shop/Detail ¦ Shipping ¦ Installation
Baseline Status |  | ✓ FROZEN — Implementation Baseline. No modifications without approved Change Request.
Governing Principle |  | Design file is the absolute source of truth. Historical data for templates only. Never override engineering.
SECTION 2 — FROZEN GOVERNING PRINCIPLES (10 Principles — Override Prohibited)
GP-01 | Live design files are the absolute engineering source of truth — never overridden by historical data
GP-02 | Historical jobs provide layout, naming, and template patterns ONLY — never engineering values
GP-03 | Every field, rule, and output must remain fully traceable to its source file, extraction rule, and agent
GP-04 | Missing engineering fields must be flagged UNRESOLVED — never guessed, defaulted, or silently filled
GP-05 | Validation severity and override governance from Phase 4 are preserved without weakening
GP-06 | Stage gate logic enforced: AB gate → GA gate → all downstream outputs. No bypass without multi-role approval
GP-07 | Unresolved items remain explicitly flagged in unresolved_issue_register — not absorbed into defaults
GP-08 | Override-prohibited fields (28 governing engineering fields) cannot be overridden under any condition
GP-09 | Audit trail mandatory for all field populations, validation results, overrides, and release gate decisions
GP-10 | Desktop-only execution — no API dependency; all modules buildable on local PostgreSQL + ChromaDB
SECTION 3 — WHAT IS FROZEN AND WHAT IS PROHIBITED
Item | Detail |  | Status
FROZEN — Database Schema | 58 modules ¦ 196 fields ¦ 10 implementation layers |  | ✓ FROZEN
FROZEN — Validation Rules | 271 rules covering all fields, stages, and cross-field dependencies |  | ✓ FROZEN
FROZEN — Override Governance | 7 override statuses ¦ 28 override-prohibited fields ¦ 42 governance matrices |  | ✓ FROZEN
FROZEN — Stage Gate Logic | 10 stage gates ¦ AB/GA hard gates ¦ Re-run cascade rules |  | ✓ FROZEN
FROZEN — Source Hierarchy | 8 source priority levels ¦ P1=Live Design → P8=Historical (presentation only) |  | ✓ FROZEN
FROZEN — Template Library | 20 patterns (P-001 to P-020) ¦ 15+ template families ¦ 8 Standard families |  | ✓ FROZEN
FROZEN — Controlled Vocabularies | 22 code lists ¦ All field enumerations reference controlled_value_master |  | ✓ FROZEN
FROZEN — Unresolved Items | 12 open items from Phase 4 — remain flagged, not absorbed into defaults |  | ✓ FROZEN
PROHIBITED — Schema Changes | No modifications to module definitions, field codes, or rule IDs without approved CR |  | ✗ BLOCKED
PROHIBITED — Rule Weakening | No reduction of validation severity, no removal of blocking flags |  | ✗ BLOCKED
PROHIBITED — Override-Prohibited Bypass | Override-prohibited fields have zero exception path — no coding workaround permitted |  | ✗ BLOCKED
PROHIBITED — Multi-version Builds | All agents must build against this single frozen baseline — no branching |  | ✗ BLOCKED

## 2. Version Register
IMPLEMENTATION VERSION REGISTER — MasterDB v3+ Baseline ¦ Phase 5 ¦ April 23, 2026
Every system component is version-controlled against this frozen baseline. No coding begins against an unregistered version.
SECTION A — COMPONENT VERSION IDENTIFIERS
Version Component | Component ID | Version Code | Frozen Version | Description | Source Document | Owner Layer | Change Control ID | Last Updated | Status
Master Database (MasterDB) | COMP-001 | MDB-V3.0 | MasterDB v3+ (Final) | Complete PostgreSQL + ChromaDB database specification with all 58 modules, 196 fields, 271 rules | MasterDB_version3_Finalized.xlsx | All Layers | BASELINE | 23-Apr-2026 | ✓ FROZEN
Database Schema Version | COMP-002 | SCH-V3.0 | Schema v3.0 | PostgreSQL table definitions for all 39 primary modules + 12 sub-registries | Module Register (Sheet 2 of MasterDB) | L1–L10 | BASELINE | 23-Apr-2026 | ✓ FROZEN
Validation Rule Version | COMP-003 | VRU-V3.0 | Rules v3.0 | 271 validation rules: 133 VR + 28 XF + 16 SG + 22 SG + 72 Override | PROMPT_4_OUTPUT + MasterDB reconciliation | L5 | BASELINE | 23-Apr-2026 | ✓ FROZEN
Field Dictionary Version | COMP-004 | FDV-V3.0 | Fields v3.0 | 196 fields F-001 to F-196 with full semantics, override status, source hierarchy | Field Dictionary sheet (MasterDB) | L3 | BASELINE | 23-Apr-2026 | ✓ FROZEN
Source Mapping Version | COMP-005 | SMP-V3.0 | Source Map v3.0 | 8 source priority levels ¦ 15 mandatory rules ¦ per-field source hierarchy | PROMPT3_OUTPUT_Source_Mapping_Foundation.xlsx | L4 | BASELINE | 23-Apr-2026 | ✓ FROZEN
Template Library Version | COMP-006 | TPL-V3.0 | Templates v3.0 | 20 template patterns P-001 to P-020 ¦ 15+ families ¦ 8 Standard families | PROMPT_0_OUTPUTTemplate_Library_Report.xlsx | L2 | BASELINE | 23-Apr-2026 | ✓ FROZEN
Controlled Vocabulary Version | COMP-007 | CVL-V3.0 | CVL v3.0 | 22 controlled vocabularies ¦ All field enumerations registered in controlled_value_master | controlled_value_master (MasterDB M-39) | L3 | BASELINE | 23-Apr-2026 | ✓ FROZEN
Override Governance Version | COMP-008 | OVR-V3.0 | Override v3.0 | 7 override statuses ¦ 42 governance matrices ¦ 28 override-prohibited fields | PROMPT_4 Override Governance Matrix | L5 | BASELINE | 23-Apr-2026 | ✓ FROZEN
Stage Gate Version | COMP-009 | SGT-V3.0 | Gates v3.0 | 10 stage gates S1–S10 ¦ AB/GA hard gates ¦ Re-run cascade rules | output_stage_gate_master (MasterDB M-33) | L7 | BASELINE | 23-Apr-2026 | ✓ FROZEN
Geometry Reconciliation Version | COMP-010 | GRC-V3.0 | Geometry v3.0 | 22 RC rules ¦ 14 tolerance rules ¦ 3 severity levels ¦ DXF↔DB check framework | MasterDB M-45 to M-48 (Prompt C Patch) | L9 | BASELINE | 23-Apr-2026 | ✓ FROZEN
Engineering Standards Version | COMP-011 | EGS-V3.0 | Eng Std v3.0 | 4 design standard branches IS/AISC/BS/EC ¦ material grade mapping ¦ seismic mapping | MasterDB M-49 to M-58 (Prompt EF Patch) | L10 | BASELINE | 23-Apr-2026 | ✓ FROZEN
Parser Version — STAAD Pro | COMP-012 | PST-V0.0 | Not yet built | Custom Python parser for .std format — HIGHEST PRIORITY build item | README.md Architecture | IT Build | CR-REQUIRED | TBD | ⏳ TO BUILD
Parser Version — MBS | COMP-013 | PMB-V0.0 | Not yet built | Custom XML/text parser for MBS export format | README.md Architecture | IT Build | CR-REQUIRED | TBD | ⏳ TO BUILD
Parser Version — ETABS | COMP-014 | PET-V0.0 | Not yet built | openpyxl + pandas Excel export parser | README.md Architecture | IT Build | CR-REQUIRED | TBD | ⏳ TO BUILD
Parser Version — Prota Steel | COMP-015 | PPR-V0.0 | Not yet built | ezdxf DXF + pdfplumber PDF report parser | README.md Architecture | IT Build | CR-REQUIRED | TBD | ⏳ TO BUILD
Backend API Version | COMP-016 | API-V0.0 | Not yet built | FastAPI REST + WebSocket backend ¦ LangGraph orchestration | README.md Stack | IT Build | CR-REQUIRED | TBD | ⏳ TO BUILD
UI Version | COMP-017 | UIV-V0.0 | Not yet built | React + TailwindCSS desktop dashboard with WebSocket live tracking | README.md Stack | IT Build | CR-REQUIRED | TBD | ⏳ TO BUILD
LLM Engine Version | COMP-018 | LLM-V0.0 | Not yet built | Ollama + Llama 3 / Mistral local deployment — no API key | README.md Stack | IT Build | CR-REQUIRED | TBD | ⏳ TO BUILD
DXF Generation Version | COMP-019 | DXF-V0.0 | Not yet built | ezdxf programmatic DXF generation from structured DB data | README.md Stack | IT Build | CR-REQUIRED | TBD | ⏳ TO BUILD
Benchmark Job Version | COMP-020 | BMK-V1.0 | BMK Set v1.0 | 3 initial benchmark projects (diverse types) — see Benchmark Register | Benchmark Register (Sheet 5) | IT Build | BASELINE | 23-Apr-2026 | ⏳ TO COMPILE
SECTION B — VERSION NUMBERING CONVENTION
Format | COMPONENT-Vx.y | x = Major version (breaking change), y = Minor version (backwards-compatible fix)
Baseline Lock | V3.0 | All frozen components are locked at V3.0. New builds start at V0.0 and increment only after CR approval.
Build Version | V0.0 → V1.0 | IT-built components start at V0.0 (not built). V1.0 = first passing build against benchmark. V2.0 = post-tuning.
Immutable Rule | BASELINE ID | Component version changes require approved Change Request. Baseline ID IFS-MASTERDB-V3-FINAL-20260423 is immutable.

## 3. Change Control Register
CHANGE CONTROL REGISTER — IFS-MASTERDB-V3-FINAL ¦ Phase 5 ¦ All changes to frozen baseline must be logged here
CHANGE CONTROL PROCESS — MANDATORY BEFORE ANY BASELINE MODIFICATION
Step 1 | CR INITIATION | Any team member identifies a required change. Logs CR with: description, affected components, reason, urgency.
Step 2 | IMPACT ASSESSMENT | IT Lead reviews: Which modules, fields, rules are affected? Does it break existing test data? Downstream cascade risk?
Step 3 | ENGINEERING REVIEW | Design Engineer reviews: Does the change affect any governing engineering field or validation rule? Is engineering justification documented?
Step 4 | APPROVAL DECISION | Change approved (IT Lead + Design Engineer sign-off required). Or rejected with reason. Or deferred to next version.
Step 5 | IMPLEMENTATION | IT implements ONLY the approved change scope. No scope creep. Version number incremented per convention.
Step 6 | REGRESSION TEST | Benchmark test suite re-run against changed components. All affected stages re-validated against baseline.
Step 7 | CR CLOSE | CR closed with outcome. Baseline ID remains IFS-MASTERDB-V3-FINAL-20260423 — patch version appended (e.g., PATCH-001).
CHANGE REQUEST LOG (Add new rows below — do not delete this header)
CR ID | Date Raised | Raised By | Component(s) Affected | COMP-ID(s) | Change Description | Impact Assessment | Engineering Review | Approval Decision | Approved By | Implementation Date | CR Status
CR-001 | 23-Apr-2026 | Phase 5 Agent | Role Model Confirmation | COMP-008 | Confirm 5 system roles: drafter, checker, design engineer, project manager, engineering lead — required before override governance can be implemented | Affects override_role_matrix (M-29) and approval_role_matrix (M-55). No code can be written for override governance until roles are confirmed. | P4 UNRESOLVED ITEM #9 — Engineering/Management input required | PENDING — Awaiting org chart input | — | — | OPEN
CR-002 | 23-Apr-2026 | Phase 5 Agent | Approval Workflow Integration | COMP-016 | Define how the approval workflow system integrates with the system — external tool vs. built-in UI flow? | Affects manual_review_trigger_master (M-30), gate_bypass_control_master (M-57). UI design and backend logic depend on this decision. | P4 UNRESOLVED ITEM #10 — IT/Workflow decision required | PENDING — Awaiting IT architecture decision | — | — | OPEN
CR-003 | 23-Apr-2026 | Phase 5 Agent | Release Authority Definition | COMP-009 | Confirm who has final authority to release drawings — Project Manager vs. Design Lead vs. dual sign-off | Affects release_authority_master (M-56), S10 gate logic. Release gate cannot be coded without this decision. | P4 UNRESOLVED ITEM #12 — Management decision required | PENDING — Awaiting management input | — | — | OPEN
CR-004 | 23-Apr-2026 | Phase 5 Agent | Member Mark Overflow Logic | COMP-004 | Define behaviour when member mark overflows (e.g., '1A' wraps to second line). Affects callout_rule_master (M-13). | Low-risk — presentation only. Does not affect engineering values. Drafting preference decision. | P4 UNRESOLVED ITEM #6 — Drafting input required | PENDING — Awaiting drafting standards input | — | — | OPEN
— LOG NEW CRs BELOW —

## 4. Defect Register
DEFECT REGISTER — IFS-MASTERDB-V3-FINAL ¦ Phase 5 ¦ All implementation defects must be logged and tracked here
DEFECT SEVERITY CLASSIFICATION
SEV-1 CRITICAL | Agent produces incorrect engineering value ¦ Validation rule not enforced ¦ Override-prohibited field bypassed ¦ Gate not blocking when it should ¦ Generation occurs without gate pass — STOP WORK immediately
SEV-2 HIGH | Audit trail incomplete ¦ Traceability path broken ¦ Fallback logic incorrect ¦ Source priority violated ¦ Stage re-run cascade not triggered correctly — Fix within current sprint
SEV-3 MEDIUM | Performance issue ¦ UI display error ¦ Non-critical field extraction failure ¦ Warning not surfaced correctly ¦ Template selection incorrect — Fix in next sprint
SEV-4 LOW | Minor UI glitch ¦ Log formatting inconsistency ¦ Non-blocking cosmetic issue ¦ Documentation mismatch — Fix before version release
DEFECT LOG (Add new rows below — do not modify headers)
Defect ID | Date Found | Found By | Stage / Agent | Severity | Defect Category | Description | Component(s) Affected | Rule/Field Ref | Root Cause | Fix Applied | Fixed By | Status
— No defects logged yet. Add rows as defects are found during implementation testing. —
DEFECT CATEGORY REFERENCE
DEF-TEMPLATE | Extraction error — wrong value from parser
DEF-VALIDATION | Validation rule not enforced correctly
DEF-OVERRIDE | Override governance breach
DEF-GATE | Stage gate not blocking or passing incorrectly
DEF-AUDIT | Audit trail missing or incomplete
DEF-TRACEABILITY | Traceability path broken
DEF-CASCADE | Re-run cascade not triggered
DEF-UI | UI display or interaction issue
DEF-PERFORMANCE | Performance below baseline
DEF-INTEGRATION | Agent-to-agent handoff failure

## 5. Benchmark Register
BENCHMARK JOB REGISTER — Phase 5 ¦ 3 Benchmark Jobs + 50 Reference Jobs ¦ Controlled Test Corpus
PURPOSE OF BENCHMARK JOBS
Benchmark jobs are the controlled standard against which the system is tested at every build milestone. They are NOT used for training or learning — they are the verification corpus. Phase 1 reference jobs (50) are used for historical learning. Benchmark jobs (minimum 3) must be diverse: simple, complex, and edge-case types. Each benchmark job must have a manually-verified gold-standard output set for comparison.
BENCHMARK JOB SPECIFICATIONS (Minimum 3 Required — Add More as System Matures)
BM ID | Job Name / Code | Building Type | Design Software | Frame Type | Key Complexity | Output Classes Required | Gold Standard Status | Folder Path | Assigned Tester | Notes
BM-001 | TBD — Standard Clear Span | Warehouse / Industrial | STAAD Pro (.std) | Clear Span Portal | Simple single-span, standard section sizes, no crane, basic bolts. Baseline for all parsers and AB/GA generation. | AB + GA + Sheeting + Shop + Shipping + Installation | NOT YET PREPARED | /Benchmark/BM-001/ | TBD | PRIORITY 1 — Must be completed before P2-03 AB agent testing begins
BM-002 | TBD — Multi-Bay with Crane | Factory / Industrial | STAAD Pro (.std) + MBS | Crane Bay (EOT) | Multi-bay, variable bay spacing (ordered list), crane system, built-up sections. Tests M-41 bay_geometry + M-42 crane_system. | AB + GA + Sheeting + Shop + Shipping + Installation | NOT YET PREPARED | /Benchmark/BM-002/ | TBD | PRIORITY 2 — Validates critical v2 gap remediations (crane + multi-bay)
BM-003 | TBD — Complex Multi-use | Mezzanine + Crane Bay | ETABS (Excel export) | Mixed (ClearSpan + Mezzanine) | Mezzanine level, multiple frame types, complex connection data, seismic zone. Tests edge cases across all output classes. | AB + GA + Sheeting + Shop + Shipping + Installation | NOT YET PREPARED | /Benchmark/BM-003/ | TBD | PRIORITY 3 — Final end-to-end validation before production release
REFERENCE JOB CORPUS (Phase 1 Historical Learning — 50 Jobs)
Ref Set | Total Jobs | Fully Parsed | Identified | Design Systems Covered | Output Classes Covered | Folder Path | QC Status | Usage Restriction | Notes
Phase 1 Reference Corpus | 50 jobs (target) | 22 jobs fully parsed | 13 jobs identified | STAAD Pro ¦ MBS ¦ ETABS ¦ Prota Steel | AB ¦ GA ¦ Sheeting ¦ Shop ¦ Shipping ¦ Installation | /Phase1_Reference/ | 97.2% complete (QC flagged exclusions enforced) | PRESENTATION PATTERNS AND TEMPLATES ONLY — Never governing engineering values | M-01 intake_job_registry + M-02 intake_sheet_registry. 3665+ sheets indexed.
BENCHMARK TEST CRITERIA — PASS / FAIL
TC ID | Output Class / Area | Test Condition | Pass Criterion | Failure Escalation
TC-001 | AB Drawing | All anchor bolt fields (F-081 to F-089) extracted correctly from design file | 100% of governing fields from P1 source | SEV-1 FAIL if any governing field from wrong source
TC-002 | GA Drawing | All grid, building, member fields consistent across AB and GA | Grid inherited correctly from approved AB | SEV-1 FAIL if GA generated before AB approved
TC-003 | Validation Gates | All stage gates fire correctly — S4 AB blocks downstream, S5 GA blocks downstream | Zero downstream generation without gate pass | SEV-1 FAIL if any gate bypass occurs without dual approval
TC-004 | Audit Trail | Every field population has 10 mandatory audit attributes logged | 100% audit completeness | SEV-2 FAIL if any mandatory attribute missing
TC-005 | Override Governance | Override-prohibited fields reject all override attempts | Zero successful overrides of prohibited fields | SEV-1 FAIL if any prohibited field can be overridden
TC-006 | Historical Isolation | No governing engineering field sourced from historical data | Zero VR-008 violations | SEV-1 FAIL if any historical value used for governing field
TC-007 | Accuracy Target | First rollout: 70-80% accuracy. Post-tuning: 80-88% | As per README accuracy expectations table | Warning if below target; review parser and field mapping
TC-008 | DXF Geometry | DXF output coordinates match DB values within geometry tolerance | 22 RC rules pass ¦ 14 tolerance rules respected | SEV-1 FAIL for Critical mismatches ¦ SEV-2 FAIL for Major

## 6. Dependency Map
IMPLEMENTATION DEPENDENCY MAP — Phase 5 ¦ Build Order + Blocking Dependencies + Parallel Tracks
CRITICAL BUILD ORDER — Sequential Gates (Must be done IN ORDER)
Build ID | Phase | Component | Description | Prerequisite(s) | Blocking Notes
BUILD-01 | INFRASTRUCTURE | Database Setup | PostgreSQL schema + ChromaDB local install + Redis + ODA File Converter + Ollama | None | ✓ PREREQUISITE — ALL agents blocked until complete
BUILD-02 | INFRASTRUCTURE | STAAD Parser | Custom Python .std parser — HIGHEST PRIORITY per README | BUILD-01 | ✓ PREREQUISITE — P2-01 Ingestion blocked until STAAD parser passes benchmark
BUILD-03 | INFRASTRUCTURE | MBS + ETABS + Prota Parsers | MBS XML/text parser ¦ ETABS openpyxl ¦ Prota ezdxf+pdfplumber | BUILD-01 | ⚠ Required before P2-01 can handle all design file types
BUILD-04 | PHASE 1 | Phase 1 Prompt Pack | Run all 5 Phase 1 prompts → populate master DB → engineering validates all outputs | BUILD-01 + BUILD-02 + BUILD-03 + 50 reference jobs compiled | ✓ PREREQUISITE — All Phase 2 agents require populated master DB
BUILD-05 | PHASE 2 | P2-01 Ingestion Agent | Design file ingestion + classification + revision conflict resolution | BUILD-04 | Gate 1 — P2-02 blocked until P2-01 PASS
BUILD-06 | PHASE 2 | P2-02 Completeness Agent | Field completeness check + Level 2 suggestions for missing fields | BUILD-05 PASS | Gate 2 — P2-03 blocked until P2-02 PASS
BUILD-07 | PHASE 2 | P2-03 AB Generation Agent | Anchor bolt plan + section + detail drawing generation (3 views) | BUILD-06 PASS | Gate 3 — P2-04 BLOCKED until P2-03 approved by engineer
BUILD-08 | PHASE 2 | P2-04 GA Generation Agent | General arrangement — inherits AB grid as fixed reference | BUILD-07 ENGINEER APPROVED | Gate 4 — Phase 3 BLOCKED until P2-04 PASS
BUILD-09 | PHASE 2 | P2-05 AB/GA Validation Gate | Hard gate — checks AB and GA together. All Phase 3 blocked on fail. | BUILD-08 PASS | HARD GATE — P2-05 FAIL = all Phase 3 stops
BUILD-10 | PHASE 3 | P3-01 Sheeting Agent | Roof and wall sheeting generation + zone coverage | BUILD-09 PASS | Parallel with P3-02, P3-03, P3-04 after gate
BUILD-11 | PHASE 3 | P3-02 Shop Drawing Agent | Fabrication-ready member drawings — connection detail registry required | BUILD-09 PASS | Parallel with P3-01, P3-03, P3-04
BUILD-12 | PHASE 3 | P3-03 Shipping List Agent | Mark-wise dispatch control — depends on shop drawing marks | BUILD-11 PASS (mark consistency) | P3-04 can parallel but P3-05 requires all P3 stages done
BUILD-13 | PHASE 3 | P3-04 Installation Drawing Agent | Erection sequence + placement drawings | BUILD-09 PASS | Parallel with P3-01, P3-02
BUILD-14 | PHASE 3 | P3-05 Final Supervisor Agent | End-to-end cross-check across ALL output classes — explicit spec in M-44 | ALL P3-01 to P3-04 PASS | FINAL GATE — Engineer approval required before output generation
BUILD-15 | OUTPUT | Output Generator Agent | ezdxf → ODA DWG → matplotlib PDF → ZIP package | BUILD-14 PASS + ENGINEER APPROVAL | Final step — no output before engineer approval
BUILD-16 | LEARNING | Level 1 Learning Agent | Rule refinement from correction_events ¦ Engineering sign-off required for all rule changes | BUILD-05 onwards (parallel background) | Level 1 first. Level 2 and 3 after Level 1 stable.
BUILD-17 | UI + API | FastAPI Backend + LangGraph + React Frontend | REST + WebSocket backend ¦ React dashboard with live tracking | BUILD-01 (can develop in parallel with BUILD-02 to BUILD-04) | UI development can proceed in parallel — agents plugged in as built
PARALLEL DEVELOPMENT TRACKS (CAN run simultaneously)
Track | Name | Build Refs | Description
TRACK A | DB + Infrastructure | BUILD-01 to BUILD-04 | Set up all infrastructure and populate master DB first. This is the critical path.
TRACK B | Parser Development | BUILD-02 + BUILD-03 | All 4 parser types can be developed in parallel. STAAD highest priority.
TRACK C | UI + API Scaffolding | BUILD-17 (parallel) | FastAPI skeleton + React dashboard can be scaffolded while agents are being built. Agents plugged in iteratively.
TRACK D | Phase 2 Sequential | BUILD-05 → BUILD-09 | MUST be sequential. Each agent depends on prior agent PASS. No parallelism within Phase 2.
TRACK E | Phase 3 (Post Gate) | BUILD-10 to BUILD-14 | P3-01 to P3-04 can run in parallel AFTER P2-05 hard gate passes. P3-05 requires all four to complete.
TRACK F | Benchmark Preparation | Parallel during BUILD-01 to BUILD-04 | Compile and verify 3 benchmark jobs with gold-standard outputs. Ready for when BUILD-05 needs testing.

## 7. Build Readiness Checklist
BUILD READINESS CHECKLIST — Phase 5 ¦ Gate before coding begins ¦ All MANDATORY items must be COMPLETE
PRE-BUILD GATE — All items below must be confirmed BEFORE any agent coding begins
Item ID | Category | Checklist Item | Priority | Owner | Status | Completion Date | Notes
RC-001 | Infrastructure | PostgreSQL installed and configured on desktop machine | MANDATORY | IT Lead | PENDING |  | Full schema from Module Register to be loaded
RC-002 | Infrastructure | ChromaDB installed locally (no cloud dependency) | MANDATORY | IT Lead | PENDING |  | Linked to PostgreSQL via project_uuid
RC-003 | Infrastructure | ODA File Converter installed (free — opendesign.com) | MANDATORY | IT Lead | PENDING |  | Required for DXF → DWG R2018 conversion
RC-004 | Infrastructure | Ollama installed with Llama 3 / Mistral model pulled | MANDATORY | IT Lead | PENDING |  | Local LLM — no API key or internet required
RC-005 | Infrastructure | Redis installed locally (Celery task queue) | MANDATORY | IT Lead | PENDING |  | Required for async execution + retry queue
RC-006 | Infrastructure | Python environment configured with all required libraries | MANDATORY | IT Lead | PENDING |  | ezdxf ¦ pdfplumber ¦ PyMuPDF ¦ Tesseract ¦ openpyxl ¦ pandas ¦ FastAPI ¦ LangGraph
RC-007 | Baseline Control | MasterDB v3+ loaded and registered as frozen baseline (IFS-MASTERDB-V3-FINAL-20260423) | MANDATORY | IT Lead + Engineering | PENDING |  | This document serves as the baseline freeze record
RC-008 | Baseline Control | Version Register completed and all COMP IDs assigned | MANDATORY | IT Lead | PENDING |  | Sheet 2 of this workbook
RC-009 | Baseline Control | Change Control Register initialized — 4 open CRs from unresolved items logged | MANDATORY | IT Lead | PENDING |  | CRs pre-logged in Sheet 3 of this workbook
RC-010 | Baseline Control | Defect Register initialized and tester assigned | MANDATORY | IT Lead | PENDING |  | Sheet 4 of this workbook
RC-011 | Governance | Engineering team has reviewed and confirmed all 10 governing principles | MANDATORY | Engineering Lead | PENDING |  | GP-01 to GP-10 from Baseline Summary
RC-012 | Governance | Role model confirmed: 5 roles (drafter, checker, design engineer, PM, engineering lead) | MANDATORY | Management | PENDING |  | CR-001 — Blocks override_role_matrix implementation
RC-013 | Governance | Release authority confirmed: who has final release sign-off | MANDATORY | Management | PENDING |  | CR-003 — Blocks S10 gate coding
RC-014 | Governance | Approval workflow decision made: external tool vs built-in | MANDATORY | IT + Management | PENDING |  | CR-002 — Affects UI and backend design
RC-015 | Reference Data | 50 reference jobs compiled into controlled source folder | MANDATORY | Engineering | PENDING |  | Phase 1 requires all 50 jobs before running Phase 1 prompt pack
RC-016 | Reference Data | 3 benchmark jobs selected, compiled, and gold-standard outputs prepared | MANDATORY | Engineering + IT | PENDING |  | See Benchmark Register — Sheet 5
RC-017 | Reference Data | STAAD Pro parser built and passing BM-001 benchmark | MANDATORY | IT Lead | PENDING |  | HIGHEST PRIORITY build — blocks P2-01
RC-018 | Parsers | MBS parser built and benchmarked | MANDATORY | IT Lead | PENDING |  | Required before full ingestion coverage
RC-019 | Parsers | ETABS parser built and benchmarked | MANDATORY | IT Lead | PENDING |  | Excel export parser — openpyxl + pandas
RC-020 | Parsers | Prota Steel parser built and benchmarked | MANDATORY | IT Lead | PENDING |  | ezdxf + pdfplumber
RC-021 | Phase 1 | Phase 1 prompt pack executed successfully — all 5 outputs validated by engineering | MANDATORY | Engineering + IT | PENDING |  | P1-01 Template Extraction ¦ P1-02 Field Dictionary ¦ P1-03 Source Mapping ¦ P1-04 Validation ¦ P1-05 Consolidator
RC-022 | Phase 1 | Master DB populated in PostgreSQL — engineering sign-off on all data | MANDATORY | Engineering Lead | PENDING |  | No Phase 2 coding until Phase 1 DB is validated
RC-023 | Optional | Member mark overflow logic decided (CR-004) | OPTIONAL | Drafting Lead | PENDING |  | Needed for callout_rule_master M-13 — low risk, can defer
RC-024 | Optional | Bolt spacing min/max tolerance table confirmed by engineering | OPTIONAL | Design Engineer | PENDING |  | P4 Unresolved Item #4 — affects VR-003 validation rule
RC-025 | Optional | Seismic standard mapping confirmed: IBC/Eurocode/IS adoption | OPTIONAL | Design Engineer | PENDING |  | P4 Unresolved Item #2 — needed before seismic_standard_mapping_master M-53
BUILD READINESS SUMMARY
Total Checklist Items |  | 25
Mandatory Items |  | 22
Optional Items |  | 3
Items COMPLETE |  | 0 (baseline freeze is step 0 — all pre-build items pending)
Items PENDING |  | 25
Build Go/No-Go Decision |  | NO-GO — Pre-build items not yet complete. Update this summary as items are resolved.
Authority to Approve Go |  | IT Lead + Engineering Lead joint sign-off required