### LANE: Lane 3 (IFS-BUILD-OUT4-UI) | DATE: 2026-04-27

#### COMPLETED WORK

Block 1 — UI Shell Foundation:

- 14-screen UI shell architecture defined and frozen (8 primary + 6 supporting views)

- 8 roles mapped with RBAC enforcement layer (drafter, checker, detailing_lead, design_engineer, pm, document_controller, qc_lead, it_admin)

- Data binding architecture confirmed for all SQLite tables (project_master, project_stage_status, validation_result, approval_request, audit_event_log, field_value_store, field_master, override_rule_master, source_priority_master)

- FastAPI WebSocket architecture scoped for live updates (gate status, approval queue, pipeline progress)

- 28 override-prohibited fields identified with lock icon + tooltip UI treatment

- Audit trail READ-ONLY mandate enforced across all 8 roles

- 4 critical screens (UI-01, UI-02, UI-04, UI-05) IN PROGRESS; 5 screens queued for Block 2; 5 screens deferred

Block 2 — Approval / Override / Audit Shell:

- 4 governance screens fully specified (UI-06 Override Request, UI-07 Approval Queue, UI-08 Audit Trail Viewer, UI-09 Source/Confidence Panel)

- Override submission event flow mapped end-to-end (submit → approval_request INSERT → audit_event_log → approver queue push)

- Quorum guard logic defined (S4/S5 gate bypass requires PM + DE approval)

- Confirmation modal mandate established (50-char minimum justification, mandatory evidence attachment)

- Role × screen access matrix completed (8 roles × 4 screens with explicit visibility rules)

- Audit visibility rules confirmed: AUDIT-READ-001 through AUDIT-PERF-001 (10 rules total, 100ms query SLA on 10K events)

Block 3 — Hold Closure Prep:

- 3 critical blockers identified with gap analysis and unblock paths

- 6 IV-2.0.0 integration layer requirements mapped (3 WebSocket event schemas, endpoint URL, auth, binding contract)

- 6 BJ-010 SQLite alignment points scoped (table names, field names, audit log schema, PRAGMA settings, DB-INIT-001 gating)

- 8-seat CCB roster structure defined with quorum and meeting cadence requirements

- 11 gap closure exit criteria itemized with owners and target dates

#### OUTPUTS GENERATED

| Output Type | Deliverable | Status | Block |
| --- | --- | --- | --- |
| Architecture Documentation | IFS-P7-UI-20260423 (FROZEN baseline) | Complete | Block 1 |
| UI Shell Specification | 14-screen UI shell with role mappings | Complete | Block 1 |
| Data Binding Specification | Screen → SQLite table bindings (8 tables) | Complete | Block 1 |
| WebSocket Integration Contract | UI-Engine Event Binding Contract | MISSING | Block 3 |
| Override Event Flow | UI-06 → UI-07 submission flow (9-step flow) | Complete | Block 2 |
| Audit Specification | AUDIT-READ-001 through AUDIT-PERF-001 (10 rules) | Complete | Block 2 |
| Role-Based Access Matrix | 8 roles × 4 screens visibility rules | Complete | Block 2 |
| Gap Analysis Report | 11 gaps, 4 categories, owners assigned | Complete | Block 3 |

#### BLOCKERS

| Blocker ID | Description | Owner | Target Unblock | Severity | Block Impact |
| --- | --- | --- | --- | --- | --- |
| B-UI-01 | IV-2.0.0 Integration Layer NOT FROZEN — WebSocket event schema unconfirmed. No UI-to-engine event binding contract exists. | Chief Architect | 2026-04-29 | CRITICAL | Blocks UI-02, UI-05, UI-07 WebSocket refresh bindings (Blocks 2–3) |
| B-UI-02 | DB-INIT-001 (Output 1) NOT YET RUN — SQLite schema not initialized. All project_stage_status, approval_request, audit_event_log reads blocked. | DB Lead | 2026-04-28 | CRITICAL | Blocks ALL SQLite-dependent UI screens (UI-01 through UI-08); prevents integration testing |
| R-UI-01 | CCB Roster 3/8 seats UNFILLED (Design Engineer, Document Controller, Independent Reviewer). Gate bypass quorum impossible. Target date OVERDUE (2026-04-25). | Program Manager | 2026-04-28 ⚠ | CRITICAL → BLOCKER | Blocks UI-06/UI-07 approval workflow sign-off; release gate authority incomplete |

Unblock Dependencies:

- B-UI-01 → unblocks UI-02/05/07 WebSocket bindings

- B-UI-02 → unblocks UI-01/02/04/05/06/07/08 SQLite table reads (highest-impact)

- R-UI-01 → unblocks approval workflow governance sign-off (escalating to blocker)

#### RISKS

| Risk ID | Description | Probability | Impact | Mitigation |
| --- | --- | --- | --- | --- |
| R-SCHEDULE | B-UI-02 (DB-INIT-001) slip beyond 2026-04-28 cascades to all Block 2 builds; integration testing cannot begin until schema is live. | HIGH | Block 2–3 build slips 2–4 days | DB Lead to prioritize DB-INIT-001 as P0; QA to confirm PASS immediately upon completion |
| R-GOVERNANCE | CCB seats unfilled for >2 days past target (2026-04-25). If UI-06/UI-07 complete before CCB established, approval workflow governance sign-off becomes critical path blocker. | HIGH | Release gate sign-off delayed 3–5 days | Program Manager to call emergency CCB session by EOD 2026-04-27 to force-close CCB-06/07/08 seat assignments |
| R-SCOPE-CREEP | IV-2.0.0 schema freeze slip or scope expansion (e.g., additional WebSocket event types) delays UI-02/05/07 builds into Block 4. | MEDIUM | Block 3 extension, Block 4 start delay | Chief Architect to publish frozen WS event schema (gates, approval, pipeline only) by 2026-04-29; no additional event types |
| R-QUERY-PERF | SQLite audit_event_log query performance SLA (100ms on 10K events) unverified until DB-INIT-001 runs; index strategy unconfirmed. | MEDIUM | AUDIT-PERF-001 test failure; UI-08 export timeout | DB Lead to pre-index project_id + event_timestamp before DB-INIT-001 confirmation |

#### PENDING WORK

| Block | Item | Status | Reason | Owner | Target |
| --- | --- | --- | --- | --- | --- |
| Block 1 | UI-01 Project Dashboard build | IN PROGRESS | Waiting B-UI-02 SQLite binding | UI Dev 1 | 2026-04-26 |
| Block 1 | UI-02 Stage Status Board build | IN PROGRESS | Waiting B-UI-02 + B-UI-01 WebSocket | UI Lead | 2026-04-27 |
| Block 1 | UI-04 Validation Results View build | IN PROGRESS | Waiting B-UI-02 SQLite binding | UI Dev 2 | 2026-04-27 |
| Block 1 | UI-05 Blocker View build | IN PROGRESS | Waiting B-UI-02 + B-UI-01 WebSocket | UI Dev 2 | 2026-04-27 |
| Block 1 | UI-BOOTSTRAP-001 acceptance test | QUEUED | Gated on B-UI-02 | UI Lead + QA | 2026-04-28 |
| Block 2 | UI-06 Override Request View build | QUEUED | Gated on B-UI-02 | UI Dev 2 | 2026-04-28 |
| Block 2 | UI-07 Approval Queue build | QUEUED | Gated on B-UI-02 + B-UI-01 | UI Lead | 2026-04-28 |
| Block 2 | UI-08 Audit Trail Viewer build | QUEUED | Gated on B-UI-02 | UI Dev 1 | 2026-04-28 |
| Block 2 | UI-09 Source/Confidence Panel build | QUEUED | No blockers; can start now | UI Dev 2 | 2026-04-29 |
| Block 2 | APPROVAL-WORKFLOW-001 integration test | QUEUED | Requires UI-06/07 complete | UI Lead + QA | 2026-04-30 |
| Block 2 | AUDIT-WRITE-001 acceptance test | QUEUED | Requires B-UI-02 + UI-08 | DB Lead + QA | 2026-04-30 |
| Block 3 | IV-2.0.0 WS event schema freeze | OPEN | Chief Architect not yet published | Chief Architect | 2026-04-29 |
| Block 3 | UI-Engine Event Binding Contract | OPEN | Document does not exist | Chief Architect | 2026-04-29 |
| Block 3 | FastAPI WS endpoint URL + auth publish | OPEN | Backend Lead not yet provided | Backend Lead | 2026-04-28 |
| Block 3 | DB-INIT-001 run + PASS confirmation | OPEN | Script not yet executed | DB Lead | 2026-04-28 |
| Block 3 | BJ-010 table/field name diff verification | OPEN | Cross-reference not yet performed | DB Lead | 2026-04-28 |
| Block 3 | CCB-06 Design Engineer seat assignment | OVERDUE | PM has not named individual | Program Manager | 2026-04-28 ⚠ |
| Block 3 | CCB-07 Document Controller seat assignment | OVERDUE | PM has not named individual | Program Manager | 2026-04-28 ⚠ |
| Block 3 | CCB-08 Independent Reviewer seat assignment | OPEN | PM has not named individual | Program Manager | 2026-04-29 |
| Block 3 | CCB weekly standing meeting scheduling | OVERDUE | Chief Architect not yet scheduled | Chief Architect | 2026-04-28 ⚠ |
| Block 3 | CCB emergency convene procedure | OPEN | Mechanism not established | Program Manager | 2026-04-29 |

#### NEXT ACTIONS

IMMEDIATE (End of 2026-04-27):

- Program Manager: Call emergency CCB session by EOD today to force-close CCB-06 (DE), CCB-07 (Doc Controller), CCB-08 (Independent Reviewer) seat assignments. Publish CCB weekly meeting schedule (recurring invite to all 8 seats).

- Chief Architect: Publish frozen WebSocket event schema (gate_status_update, approval_queue_update, pipeline_progress) with field definitions and envelope structure by EOD 2026-04-29.

- DB Lead: Execute DB-INIT-001 initialization script immediately; confirm PASS status and notify UI team. Run BJ-010 table/field name cross-reference against MasterDB v3+ baseline; produce diff report.

SHORT-TERM (2026-04-28): 4. Backend Lead: Publish FastAPI WebSocket endpoint URL + auth mechanism to UI team by EOD 2026-04-28. 5. UI Dev 2: Unblock by B-UI-02 clearance: begin UI-09 Source/Confidence Panel build (no blockers; can run in parallel). 6. QA Lead: Prepare AUDIT-WRITE-001 and AUDIT-PERF-001 test harnesses; await DB-INIT-001 PASS to begin execution. 7. Chief Architect: Schedule CCB weekly standing meeting (recurring); establish emergency convene procedure (contact list, decision threshold, record format).

CRITICAL PATH (2026-04-29–2026-04-30): 8. Chief Architect: Deliver UI-Engine Event Binding Contract (signed) by 2026-04-29; formally close B-UI-01. 9. DB Lead: Confirm DB-INIT-001 PASS; formally close B-UI-02 by 2026-04-28 (enables Block 2 full mobilization). 10. Program Manager: Issue CCB-ROSTER-CONFIRMED notice; formally close R-UI-01 by 2026-04-29. 11. UI Lead + QA: Run UI-BOOTSTRAP-001 acceptance test (Block 1 exit criterion) by 2026-04-28. 12. UI Lead + QA: Run APPROVAL-WORKFLOW-001 + AUDIT-WRITE-001 integration tests (Block 2 exit criteria) by 2026-04-30.

#### NEXT START POINT

For 2026-04-28 Morning Standup:

- Status Check (first 15 min):

  - DB Lead: Confirm DB-INIT-001 PASS status (yes/no; if no, provide revised ETA)

  - Program Manager: Confirm all 3 CCB seats (06/07/08) named and accepted (yes/no; if no, escalate)

  - Chief Architect: Confirm WS event schema published for review (yes/no; if no, provide draft for interim binding work)

- Unblock Decision (next 10 min):

  - If B-UI-02 PASS: Release UI-01, UI-02, UI-04, UI-05, UI-06, UI-07, UI-08 to full build (SQLite bindings live)

  - If B-UI-02 PENDING: Continue with offline UI logic (no DB reads); UI-09 proceeds (no SQL dependency)

  - If R-UI-01 CLOSED: Release UI-06/07 governance sign-off path

- Parallel Track Activation:

  - If B-UI-02 PASS + R-UI-01 CLOSED: Block 2 full mobilization; allocate all UI devs to UI-06, UI-07, UI-08, UI-09 builds

  - If B-UI-01 PENDING: Build UI-02/05/07 quorum/blocker logic offline; defer WebSocket bindings to Block 4

  - If CCB seats unfilled: Escalate to CTO; freeze approval workflow sign-off to Phase 5b

- Deliverables Due 2026-04-28 EOD:

  - DB-INIT-001 PASS confirmation (or revised date)

  - WS event schema frozen document (Chief Architect)

  - FastAPI endpoint URL + auth (Backend Lead)

  - BJ-010 table/field name diff report (DB Lead)

  - CCB roster complete + weekly meeting scheduled (Program Manager)

  - UI-BOOTSTRAP-001 test results (UI Lead + QA)

- Block 3 Hold Closure:

  - Cannot proceed to Block 4 (Integration Testing / IV-2.0.0) until:

    - ✓ B-UI-01 CLOSED (WS schema frozen, binding contract signed)

    - ✓ B-UI-02 CLOSED (DB-INIT-001 PASS confirmed)

    - ✓ R-UI-01 CLOSED (CCB fully seated and meeting cadence active)

#### STATUS: 🔴 RED

Justification:

- 3 CRITICAL blockers active (B-UI-01, B-UI-02, R-UI-01); cannot proceed with Block 2 SQLite or WebSocket bindings until resolved

- Governance escalation: R-UI-01 OVERDUE by 2 days (target 2026-04-25; still unfilled 2026-04-27); gate bypass quorum physically impossible

- Block 2 entry gated on 2 dependencies: B-UI-02 (DB) + B-UI-01 (IV-2.0.0) both unmet; full mobilization blocked

- Integration testing cannot begin: DB schema not initialized; UI-Engine binding contract missing

- High-risk schedule compression: CCB seat assignments, WS schema freeze, and DB-INIT-001 all due within 24–48 hours with no confirmed ETAs

Path to AMBER: All 3 blockers must show clear unblock progress by EOD 2026-04-28 (B-UI-02 and R-UI-01 CLOSED; B-UI-01 schema draft published).

#### BASELINE DEVIATION

YES — 2 deviations from IFS-P7-UI-20260423 baseline:

- R-UI-01 escalation: CCB roster target date (2026-04-25) missed by 2 days. Risk was rated manageable at Block 1 closure; now escalating to BLOCKER status as approval workflow screens approach completion. Mitigation: Emergency CCB session required by EOD 2026-04-27.

- IV-2.0.0 freeze delay: Block 3 analysis reveals UI-Engine Event Binding Contract document does not exist. Baseline assumed contract would be in place by 2026-04-27; actual delivery now targeted 2026-04-29. Impact: WebSocket bindings (UI-02, UI-05, UI-07) deferred from Block 2 to Block 4. Mitigation: Chief Architect to deliver frozen schema + contract simultaneously by 2026-04-29.

No other baseline deviation. All screen scopes, role mappings, data binding architectures, and audit rules remain aligned with IFS-P7-UI-20260423 frozen baseline.