## SQLite Core Schema Build
LANE 1 — BLOCK 1 │ SQLite Core Schema Build Tracker
Steel Detailing Desktop System · Frozen Baseline · Lane 1 Execution Pack
|  |  | Prepared by: | Lane 1 Block 1 Agent | Date: | 2026-04-27 | v1.0
# | Table / Component | Category | Status | FK / PK | Constraint Type | Notes / Complications | Owner / Assignee
── SECTION 1: CORE PROJECT TABLES ──
1 | project_master | Core Table | ✅ Created | ✅ Verified | PK · UNIQUE · CHECK | project_code UNIQUE; is_active CHECK(0,1); auto-stamp updated_at via trigger | Lane 1 Agent
2 | module_registry | Core Table | ✅ Created | ✅ Verified | PK · UNIQUE · CHECK | module_name UNIQUE; is_enabled CHECK(0,1) | Lane 1 Agent
3 | field_dictionary | Core Table | ✅ Created | ✅ Verified | PK · FK → module_registry · UNIQUE · CHECK | (module_id, field_name) composite UNIQUE; allowed_values JSON array for ENUMs; FK RESTRICT on delete | Lane 1 Agent
── SECTION 2: RULE ENGINE TABLES ──
4 | validation_rule_master | Rule Engine | ✅ Created | ✅ Verified | PK · FK × 2 · CHECK | severity CHECK enforced; layer & stage_scope columns ready for engine routing; FK on module_id RESTRICT, field_id SET NULL | Lane 1 Agent
── SECTION 3: SOURCE MAPPING TABLES ──
5 | source_mapping_master | Source Mapping | ✅ Created | ✅ Verified | PK · FK → field_dictionary · UNIQUE | (field_id, source_system) UNIQUE; FK CASCADE on delete; priority ordinal column | Lane 1 Agent
6 | source_fallback_chain | Source Mapping | ✅ Created | ✅ Verified | PK · FK → field_dictionary · UNIQUE | (field_id, fallback_order) UNIQUE; ordered fallback sequence; FK CASCADE on delete | Lane 1 Agent
── SECTION 4: STAGE & RESULT TABLES ──
7 | project_stage_status | Stage Gate | ✅ Created | ✅ Verified | PK · FK → project_master · UNIQUE · CHECK | stage CHECK S1–S10; gate_status CHECK(PENDING/OPEN/PASSED/BLOCKED/LOCKED); gate_result_json stores full snapshot | Lane 1 Agent
8 | validation_result | Result Store | ✅ Created | ✅ Verified | PK · FK × 3 · CHECK | outcome CHECK; severity_applied CHECK; run_id groups engine runs; field_value_snap captures value at validation time | Lane 1 Agent
── SECTION 5: AUDIT TABLE ──
9 | audit_event_log | Audit / Immutable | ✅ Created | ✅ Verified | PK · FK → project_master · CHECK | is_immutable CHECK(=1); protected by trg_audit_no_update and trg_audit_no_delete; live-tested and confirmed ABORT on UPDATE and DELETE | Lane 1 Agent
── SECTION 6: PRAGMA SETTINGS ──
P1 | journal_mode = WAL | PRAGMA | ✅ Created | N/A | Runtime Setting | Confirmed: PRAGMA returns 'wal'; required for concurrent reads during engine run | Lane 1 Agent
P2 | foreign_keys = ON | PRAGMA | ✅ Created | N/A | Per-Connection Setting | Must be re-issued on each DB connection open. Engine init routine must include this. | Lane 1 Agent
P3 | synchronous = NORMAL | PRAGMA | ✅ Created | N/A | Runtime Setting | Balances write durability and performance for WAL mode | Lane 1 Agent
P4 | temp_store = MEMORY | PRAGMA | ✅ Created | N/A | Runtime Setting | Keeps temp tables in memory for engine speed | Lane 1 Agent
P5 | cache_size = -32000 | PRAGMA | ✅ Created | N/A | Runtime Setting | 32 MB cache; suitable for project-scale validation runs | Lane 1 Agent
P6 | auto_vacuum = INCREMENTAL | PRAGMA | ✅ Created | N/A | Runtime Setting | Prevents DB file bloat over iterative run sessions | Lane 1 Agent
P7 | integrity_check | PRAGMA | ✅ Created | N/A | Verification | Confirmed: returns 'ok' after full schema build | Lane 1 Agent
P8 | foreign_key_check | PRAGMA | ✅ Created | N/A | Verification | Confirmed: no violations on fresh schema | Lane 1 Agent
── SECTION 7: TRIGGERS ──
T1 | trg_audit_no_update | Trigger / Immutable | ✅ Created | N/A | BEFORE UPDATE | ABORT with 'IMMUTABLE: audit_event_log rows cannot be updated.' — live-tested ✅ | Lane 1 Agent
T2 | trg_audit_no_delete | Trigger / Immutable | ✅ Created | N/A | BEFORE DELETE | ABORT with 'IMMUTABLE: audit_event_log rows cannot be deleted.' — live-tested ✅ | Lane 1 Agent
T3 | trg_pm_updated_at | Trigger / Auto-stamp | ✅ Created | N/A | AFTER UPDATE | Auto-stamps updated_at on project_master when not manually set | Lane 1 Agent
T4 | trg_pss_updated_at | Trigger / Auto-stamp | ✅ Created | N/A | AFTER UPDATE | Auto-stamps updated_at on project_stage_status | Lane 1 Agent
T5 | trg_vrm_updated_at | Trigger / Auto-stamp | ✅ Created | N/A | AFTER UPDATE | Auto-stamps updated_at on validation_rule_master | Lane 1 Agent
── SECTION 8: INDEXES ──
I1 | idx_vr_project_stage | Index | ✅ Created | N/A | Composite | validation_result(project_id, stage) | Lane 1 Agent
I2 | idx_vr_run_id | Index | ✅ Created | N/A | Single Col | validation_result(run_id) | Lane 1 Agent
I3 | idx_vr_rule_id | Index | ✅ Created | N/A | Single Col | validation_result(rule_id) | Lane 1 Agent
I4 | idx_pss_project | Index | ✅ Created | N/A | Single Col | project_stage_status(project_id) | Lane 1 Agent
I5 | idx_ael_project | Index | ✅ Created | N/A | Single Col | audit_event_log(project_id) | Lane 1 Agent
I6 | idx_ael_event_type | Index | ✅ Created | N/A | Single Col | audit_event_log(event_type) | Lane 1 Agent
I7 | idx_ael_occurred_at | Index | ✅ Created | N/A | Single Col | audit_event_log(occurred_at) | Lane 1 Agent
I8 | idx_fd_module | Index | ✅ Created | N/A | Single Col | field_dictionary(module_id) | Lane 1 Agent
I9 | idx_vrm_layer | Index | ✅ Created | N/A | Single Col | validation_rule_master(layer) | Lane 1 Agent
I10 | idx_vrm_severity | Index | ✅ Created | N/A | Single Col | validation_rule_master(severity) | Lane 1 Agent
BLOCK STATUS SUMMARY
Total Items | ✅ Created | ⚠️ Partial | ❌ Not Created | 🔁 In Progress | 🔒 Blocked | Block Status | Agent Sign-off
32 | 32 | 0 | 0 | 0 | 0 | 🟢 GREEN | Lane 1 Block 1 Agent
STATUS LEGEND: ✅ Created = confirmed in DB ⚠️ Partial = schema exists but incomplete ❌ Not Created = missing 🔁 In Progress = actively being built 🔒 Blocked = cannot proceed