## Layers Completed
LANE 1 — BLOCK 3 │ Core Layers and Hard Gates
Steel Detailing Desktop System · Validation Layer Implementation · Lane 1 Block 3
|  |  | Prepared by: | Lane 1 Block 3 Agent | Date: | 2026-04-27 | v1.0
# | Layer Module | Scope | Build Status | Test Status | Entry Point | Notes / Detail | Owner
── SECTION 1: CORE VALIDATION LAYERS (L01–L05) ──
1 | layer_01_completeness | Completeness | ✅ Complete | ✅ Tested | evaluate(rule, field_value) | Checks required fields are non-null and non-empty. Returns FAIL if field is None or whitespace-only. Used as first-pass gate across all stages. | Lane 1 Agent
2 | layer_02_datatype | Data Type | ✅ Complete | ✅ Tested | evaluate(rule, field_value, declared_type) | Validates against declared_type: TEXT/INTEGER/REAL/BOOLEAN/DATE. Uses regex for DATE (ISO 8601). Defaults to TEXT if type unknown. | Lane 1 Agent
3 | layer_03_unit | Unit | ✅ Complete | ✅ Tested | evaluate(rule, field_value, unit_type) | Validates unit labels against known_units dict keyed by unit_type (length/mass/force/angle/generic). Returns FAIL if unit not in allowed set. | Lane 1 Agent
4 | layer_04_enumeration | Enumeration | ✅ Complete | ✅ Tested | evaluate(rule, field_value, allowed_values_json) | Parses allowed_values JSON array from field_dictionary. Returns FAIL if value not in set. Returns SKIP if no enum constraint defined. | Lane 1 Agent
5 | layer_05_format | Format / Regex | ✅ Complete | ✅ Tested | evaluate(rule, field_value) | Uses rule_expression column as regex pattern (fullmatch). Returns SKIP if no pattern defined. Handles invalid regex gracefully. | Lane 1 Agent
── SECTION 2: STAGE GATE LAYER (L10) ──
6 | layer_10_stage_gate | Stage Gate | ✅ Complete | ✅ Tested | evaluate_gate(stage, blocker_registry, stage_statuses) | Combines prerequisite check + blocker check into final gate status. HARD GATE enforced for S4 and S5 — any BLOCKER/RELEASE_BLOCKER → unconditional BLOCKED. | Lane 1 Agent
P | PREREQUISITE_MAP | Gate Config | ✅ Complete | ✅ Tested | check_prerequisites(stage, stage_statuses) | Maps S2→[S1], S3→[S1,S2], S4→[S1-S3], S5→[S1-S4], S6→[S5], S7→[S5,S6], S8→[S5-S7], S9→[S5-S8], S10→[S5-S9]. BLOCKED if any prerequisite not PASSED. | Lane 1 Agent
BLOCK 3 STATUS SUMMARY
Total | ✅ Complete | ⚠️ Partial | ❌ Not Built | 🔁 In Progress | 🔒 Blocked | Block Status | Sign-off
7 | 7 | 0 | 0 | 0 | 0 | 🟢 GREEN | Lane 1 Block 3 Agent

## Hard-Gate Status
LANE 1 — BLOCK 3 │ S4 & S5 Hard-Gate Status
Confirms hard-gate blocking is intact for release-critical stages
|  |  | Prepared by: | Lane 1 Block 3 Agent | Date: | 2026-04-27 | v1.0
# | Stage | Gate Type | BLOCKER → | RELEASE_BLOCKER → | Gate Result | Behavior / Rule | Verified
── S4 HARD GATE ──
1 | S4 | HARD GATE | BLOCKED | BLOCKED | BLOCKED | Any BLOCKER or RELEASE_BLOCKER fail unconditionally locks S4. Cannot be overridden at engine level. Prerequisite: S1+S2+S3 all PASSED. | ✅ Verified
2 | S4 | HARD GATE — PASS condition | 0 fails | 0 fails | PASSED | gate_status=PASSED only when zero BLOCKER/RELEASE_BLOCKER fails AND all prerequisites PASSED. Errors/Warnings allowed. | ✅ Verified
3 | S4 | HARD GATE — prereq fail | N/A | N/A | BLOCKED | If S1/S2/S3 not PASSED → BLOCKED with message listing missing stages. Evaluated first before rule-level checks. | ✅ Verified
── S5 HARD GATE ──
4 | S5 | HARD GATE | BLOCKED | BLOCKED | BLOCKED | Same hard-gate enforcement as S4. S5 additionally requires S4=PASSED. Any BLOCKER/RELEASE_BLOCKER → BLOCKED. Release-critical stage. | ✅ Verified
5 | S5 | HARD GATE — PASS condition | 0 fails | 0 fails | PASSED | gate_status=PASSED only when S1–S4 all PASSED AND zero blockers. All layer outputs must be PASS or SKIP. | ✅ Verified
── NON-HARD-GATE STAGES ──
6 | S1 | STANDARD | BLOCKED | BLOCKED | BLOCKED | S1 has no prerequisites. Still BLOCKED on BLOCKER/RELEASE_BLOCKER fails. Not a hard gate — future override mechanism could be applied. | ✅ Verified
7 | S2–S3 | STANDARD | BLOCKED | BLOCKED | BLOCKED | Sequential prerequisites enforced. Not hard gates but BLOCKER/RELEASE_BLOCKER still cause BLOCKED status. | ✅ Verified
8 | S6–S10 | STANDARD | BLOCKED | BLOCKED | BLOCKED | All post-S5 stages require S5=PASSED as prerequisite baseline. BLOCKER/RELEASE_BLOCKER cause BLOCKED. | ✅ Verified

## Prerequisite Logic Status
LANE 1 — BLOCK 3 │ Prerequisite Logic Status
Stage prerequisite map and enforcement verification
|  |  | Prepared by: | Lane 1 Block 3 Agent | Date: | 2026-04-27 | v1.0
# | Stage | Prerequisites Required | Prerequisites Logic | Status | Audit Write | Notes | Verified
1 | S1 | None (entry stage) | No check required — S1 is the initial stage | ✅ Verified | ✅ Yes | Gate result written to project_stage_status; audit_event_log entry on GATE_TRANSITION | ✅ Verified
2 | S2 | S1 = PASSED | check_prerequisites returns BLOCKED if S1 ≠ PASSED | ✅ Verified | ✅ Yes | Audit event written with detail JSON including missing stages list | ✅ Verified
3 | S3 | S1, S2 = PASSED | BLOCKED if either S1 or S2 ≠ PASSED | ✅ Verified | ✅ Yes | Prerequisite gate evaluated before rule-level checks in evaluate_gate() | ✅ Verified
4 | S4 | S1, S2, S3 = PASSED | HARD GATE — BLOCKED if any S1–S3 ≠ PASSED | ✅ Verified | ✅ Yes | S4 is a hard gate: prerequisite check + blocker check both enforced | ✅ Verified
5 | S5 | S1–S4 = PASSED | HARD GATE — BLOCKED if any S1–S4 ≠ PASSED | ✅ Verified | ✅ Yes | S5 is a hard gate: S4 must be PASSED first — cannot skip via override | ✅ Verified
6 | S6 | S5 = PASSED | BLOCKED if S5 ≠ PASSED | ✅ Verified | ✅ Yes | Post-release gate; S5 PASSED is the baseline for all S6–S10 | ✅ Verified
7 | S7 | S5, S6 = PASSED | BLOCKED if either ≠ PASSED | ✅ Verified | ✅ Yes | Sequential enforcement continues post-S5 | ✅ Verified
8 | S8 | S5, S6, S7 = PASSED | BLOCKED if any ≠ PASSED | ✅ Verified | ✅ Yes |  | ✅ Verified
9 | S9 | S5, S6, S7, S8 = PASSED | BLOCKED if any ≠ PASSED | ✅ Verified | ✅ Yes |  | ✅ Verified
10 | S10 | S5–S9 = PASSED | BLOCKED if any S5–S9 ≠ PASSED | ✅ Verified | ✅ Yes | Final closeout gate; full chain must be PASSED | ✅ Verified
A | Audit on GATE_TRANSITION | All stages | AuditWriter.write(event_type='GATE_TRANSITION', ...) | ✅ Verified | ✅ Yes | Writes project_id, run_id, gate_status, full gate_result JSON to audit_event_log (immutable) | ✅ Verified
B | Audit on validation_result | All rules | engine_core._write_result() per rule | ✅ Verified | ✅ Yes | One validation_result row per rule per run. run_id groups batch for traceability. | ✅ Verified

## Blockers & Next Block Readiness
LANE 1 — BLOCK 3 │ Blockers & Next Block Readiness
Open issues, risks, and Block 4 start conditions
# | Category | Severity | Status | Detail | Action / Owner
1 | Blocker | ℹ️ Info | 🟢 Resolved | Block 3 has zero open blockers. All six layer modules built, syntax-checked, and functionally tested. | No action required — Lane 1 Agent
2 | Advisory — PRAGMA | 🟡 Medium | 🟢 Resolved | foreign_keys = ON must be re-issued per DB connection. Engine init routine must include this PRAGMA on every connection open. | Confirm in engine_core.get_connection() — Lane 1 Agent
3 | Advisory — Layers L06–L09, L11–L13 | 🟠 High | 🟡 In Progress | Advanced layers (dependency, cross-field, source governance, override, fallback, geometry RC) are defined in Block 6. Layer dispatch in engine_core currently uses stub evaluator. | Block 6 Agent to implement advanced layers and register them in engine dispatch — Lane 1 Agent
4 | Advisory — Audit write dependency | ℹ️ Info | 🟢 Resolved | audit_writer confirmed to write gate transition events. Validation result rows written per-rule via engine_core._write_result(). Immutable audit trigger live-tested (Block 1). | No action — Lane 1 Agent
5 | Next Block Dependency | 🟢 Low | 🟢 Resolved | Block 4 (Lane Packaging Note) can start immediately. All Block 1–3 outputs are complete. | Lane 1 Block 4 Agent to consolidate and package — Lane 1 Agent
6 | Next Block Dependency | 🟢 Low | 🟢 Resolved | Block 5 (Seed Data, Migration, Initialization) has no dependency on Block 3 runtime layers — can run in parallel. | Lane 1 Block 5 Agent — Lane 1 Agent