LANE 3 · BLOCK 3 AGENT Hold Closure Prep — Progress Note Ref: IFS-BUILD-OUT4-UI-20260424 ¦ Baseline: IFS-P7-UI-20260423 / MasterDB v3+ ¦ Date: 2026-04-27

## Hold Items Overview

| Hold Item | Description | Current Status | Target Date | Owner |
| --- | --- | --- | --- | --- |
| B-UI-01 / IV-2.0.0 | Integration layer freeze — WebSocket event schema must be confirmed and frozen before UI bindings can be wired | OPEN — schema unconfirmed | 2026-04-29 | Chief Architect |
| B-UI-02 / BJ-010 | SQLite schema alignment — DB-INIT-001 must pass; BJ-010 wording must align with MasterDB v3+ frozen schema | OPEN — DB-INIT-001 pending | 2026-04-28 | DB Lead |
| R-UI-01 / CCB | CCB roster 3/8 seats unfilled — governance authority cannot be established until quorum roster is complete | OVERDUE — target was 2026-04-25 | 2026-04-25 ⚠ | Program Manager |

# 1. IV-2.0.0 Prep Status

## 1a. Freeze Requirements Review

| IV-2.0.0 Requirement | Detail | Current Gap | Gap Owner | Status |
| --- | --- | --- | --- | --- |
| WS Event Schema — Gate Status Update | FastAPI WebSocket must emit gate_status_update event with fields: project_id, gate_id, gate_status, timestamp, blocker_count | Event schema NOT CONFIRMED — field names, types, envelope structure undefined | Chief Architect | BLOCKED |
| WS Event Schema — Approval Queue Push | WebSocket must emit approval_queue_update event: request_id, approver_role, status, timestamp | Approval push schema NOT CONFIRMED | Chief Architect | BLOCKED |
| WS Event Schema — Pipeline Progress | WebSocket must emit pipeline_progress event: stage_id, pct_complete, active_rule_count | Pipeline progress schema NOT CONFIRMED | Chief Architect | BLOCKED |
| WS Connection Endpoint | FastAPI endpoint URL and auth mechanism must be defined — UI-02, UI-05, UI-07 bind to it | Endpoint URL and auth not specified | Backend Lead | BLOCKED |
| WS Propagation SLA | Gate status update must reach all connected clients within 2 seconds (Acceptance criterion #11) | SLA agreed in spec; not yet testable — no WS endpoint | Backend Lead | PENDING |
| UI-Engine Event Binding Contract | Formal contract specifying event names, payload schemas, error handling, and reconnect behaviour | Contract document does not exist yet | Chief Architect | MISSING |

## 1b. Required Actions to Unfreeze IV-2.0.0

| # | Required Action | Owner | Target | Unblocks |
| --- | --- | --- | --- | --- |
| IV-1 | Define and freeze WebSocket event schema for gate_status_update, approval_queue_update, pipeline_progress | Chief Architect | 2026-04-29 | UI-02 WS binding, UI-05 blocker push, UI-07 approval push |
| IV-2 | Publish FastAPI WebSocket endpoint URL + auth mechanism to UI team | Backend Lead | 2026-04-28 | UI Lead can wire WebSocket client in UI-02, UI-07 |
| IV-3 | Produce formal UI-Engine Event Binding Contract document — signed by Chief Architect | Chief Architect | 2026-04-29 | IV-2.0.0 integration layer freeze; B-UI-01 clearance |
| IV-4 | Run 2-second propagation SLA test against live WS endpoint with 10 connected clients | QA Lead | 2026-04-30 | Acceptance criterion #11 sign-off |

IV-2.0.0 STATUS: BLOCKED — 3 of 6 requirements missing; contract document does not exist Chief Architect must deliver frozen WS event schema by 2026-04-29 or Block 2 WebSocket bindings slip to Block 4. All UI screens except UI-09 have at least one binding dependent on IV-2.0.0 clearance.

# 2. BJ-010 Prep Status

## 2a. BJ-010 SQLite Alignment Review

| BJ-010 Element | Current Wording (Inferred from Out4 Doc) | Required MasterDB v3+ Alignment | Gap | Status |
| --- | --- | --- | --- | --- |
| Schema Reference | References IFS-P7-UI-20260423 UI schema | Must explicitly cite MasterDB v3+ as the authoritative schema baseline; TDN-DB-001 Approved | Schema citation may not match frozen DB baseline | NEEDS VERIFICATION |
| Table Names | Uses UI-layer table name references | Must align exactly with MasterDB v3+ frozen table names: project_master, project_stage_status, validation_result, approval_request, approval_decision, audit_event_log, field_value_store, field_master, override_rule_master, source_priority_master | Any divergence in table naming breaks DB-INIT-001 init scripts | NEEDS CONFIRMATION |
| Field Names | Field names referenced from P7 doc | Must match MasterDB v3+ frozen field names exactly — especially: gate_status, severity, generation_blocked, is_override_prohibited, confidence_pct, priority_rank | Naming delta between BJ-010 wording and MasterDB v3+ would cause runtime binding failures | NEEDS CONFIRMATION |
| Audit Log Schema | audit_event_log referenced for READ-ONLY mandate | 10 mandatory attributes confirmed: event_id, timestamp, project_id, field_id, event_type, actor_role, actor_id, before_value, after_value, source_reference — must appear in BJ-010 verbatim | Attribute list may be incomplete in BJ-010 | NEEDS VERIFICATION |
| PRAGMA Settings | PRAGMA settings referenced in UI-14 System Config | BJ-010 must specify: journal_mode=WAL, foreign_keys=ON, synchronous=FULL — must match MasterDB v3+ initialization sequence | PRAGMA alignment not confirmed | NEEDS CONFIRMATION |
| DB-INIT-001 Reference | DB-INIT-001 cited as gating item | BJ-010 must explicitly state: 'UI binding to all SQLite tables is conditional on DB-INIT-001 PASS status' | Dependency statement may be implicit, not explicit | NEEDS EXPLICIT WORDING |

## 2b. Required Actions to Close BJ-010

| # | Required Action | Owner | Target | Risk if Missed |
| --- | --- | --- | --- | --- |
| BJ-1 | DB Lead to cross-reference BJ-010 table names against MasterDB v3+ schema — produce diff report | DB Lead | 2026-04-28 | Silent naming mismatch causes runtime table-not-found errors in production |
| BJ-2 | DB Lead to cross-reference BJ-010 field names against MasterDB v3+ frozen fields — especially audit_event_log and field_value_store | DB Lead | 2026-04-28 | Field binding failures at UI layer; confidence_pct / priority_rank mismatch breaks UI-09 |
| BJ-3 | DB Lead to confirm PRAGMA settings in BJ-010 match MasterDB v3+ init sequence exactly | DB Lead | 2026-04-28 | SQLite integrity settings diverge between BJ-010 and actual DB — data corruption risk |
| BJ-4 | DB Lead to add explicit BJ-010 wording: 'UI binding to all SQLite tables conditional on DB-INIT-001 PASS status' | DB Lead | 2026-04-28 | Ambiguity in gating condition; UI team may attempt premature binding |
| BJ-5 | DB Lead to run DB-INIT-001 initialization script; confirm PASS status; notify UI team | DB Lead | 2026-04-28 | All Block 2 + Block 3 SQLite reads remain blocked; UI shell cannot be integration-tested |

BJ-010 STATUS: VERIFICATION IN PROGRESS — DB-INIT-001 not yet confirmed PASS 5 alignment points need DB Lead cross-reference against MasterDB v3+. None are confirmed complete. Until DB-INIT-001 PASS is confirmed, ALL SQLite-dependent UI screens (UI-01 through UI-08) cannot be integration-tested.

# 3. CCB Prep Status

## 3a. CCB Roster Review

| Seat # | Required Role | Quorum Function | Named Individual | Confirmation Status |
| --- | --- | --- | --- | --- |
| CCB-01 | Chief Architect | Technical veto authority; approves IV-2.0.0 freeze | CONFIRMED | ✓ FILLED |
| CCB-02 | UI/Frontend Team Lead | Approves UI shell scope changes and deferrals | CONFIRMED | ✓ FILLED |
| CCB-03 | DB Lead | Approves schema changes; DB-INIT-001 authority | CONFIRMED | ✓ FILLED |
| CCB-04 | QA Lead | Acceptance test authority; gate sign-off | CONFIRMED | ✓ FILLED |
| CCB-05 | Program Manager | Schedule authority; risk acceptance | CONFIRMED | ✓ FILLED |
| CCB-06 | Design Engineer | Engineering authority; override approval governance | NOT NAMED ⚠ | ✗ UNFILLED |
| CCB-07 | Document Controller | Release gate authority; document sign-off | NOT NAMED ⚠ | ✗ UNFILLED |
| CCB-08 | Independent Reviewer | External technical review; no change authority | NOT NAMED ⚠ | ✗ UNFILLED |

## 3b. Quorum and Cadence Requirements

| Quorum Requirement | Detail | Current State | Risk |
| --- | --- | --- | --- |
| Minimum quorum for gate bypass approval | BOTH Design Engineer (CCB-06) AND Program Manager (CCB-05) must approve S4/S5 gate bypass requests | PM confirmed (CCB-05); DE seat UNFILLED (CCB-06) | CRITICAL — quorum physically impossible until DE seat filled |
| Minimum quorum for schema change approval | Chief Architect + DB Lead + at least one other CCB member | 3 of 5 required seats filled — quorum achievable for schema changes only | MODERATE — workable but fragile |
| Full board authority for release sign-off | 5 of 8 CCB members must vote; all 8 must be named | Only 5 of 8 seats named — formal release sign-off not achievable | CRITICAL — release gate blocked |
| CCB meeting cadence | Weekly standing meeting required per governance spec; chair = Chief Architect | Cadence NOT ESTABLISHED — no standing meeting scheduled | HIGH RISK — governance timeline compressed |
| Emergency CCB (24hr convene) | Any member may call emergency session for release-blocking items | Mechanism not yet established; contact list incomplete | MODERATE |

## 3c. Required Actions to Establish CCB

| # | Required Action | Owner | Target | Consequence if Missed |
| --- | --- | --- | --- | --- |
| CCB-1 | PM to name and confirm CCB-06 (Design Engineer) — individual must accept governance role formally | Program Manager | 2026-04-28 | Gate bypass quorum impossible; UI-07 approval workflow cannot be signed off; R-UI-01 escalates to blocker |
| CCB-2 | PM to name and confirm CCB-07 (Document Controller) for release gate authority | Program Manager | 2026-04-28 | Release control (UI-11) sign-off chain incomplete |
| CCB-3 | PM to name and confirm CCB-08 (Independent Reviewer) — external candidate or nominated internal | Program Manager | 2026-04-29 | Full board quorum unachievable; formal release sign-off blocked |
| CCB-4 | Chief Architect to schedule weekly CCB standing meeting — recurring calendar invite to all 8 seats | Chief Architect | 2026-04-28 | Governance decisions bottleneck on ad-hoc scheduling; change backlog grows |
| CCB-5 | PM to establish emergency CCB convene procedure — contact list, decision threshold, record format | Program Manager | 2026-04-29 | No fast-path for release-blocking decisions; critical path slippage |
| CCB-6 | PM to formally close R-UI-01 — confirm all 8 seats named; issue CCB-ROSTER-CONFIRMED notice | Program Manager | 2026-04-29 | R-UI-01 converts from RISK to BLOCKER if approval workflow screens are ready before CCB is established |

CCB STATUS: OVERDUE — TARGET DATE 2026-04-25 PASSED. R-UI-01 ESCALATION IMMINENT. 3 of 8 CCB seats unfilled. Gate bypass quorum (CCB-06 DE + CCB-05 PM) physically impossible until DE seat is named. Weekly standing meeting not scheduled. Emergency convene procedure does not exist. If UI-06 and UI-07 complete build before CCB is established, approval workflow governance sign-off will be the critical path blocker.

# 4. Remaining Gaps

| Gap ID | Gap Description | Category | Severity | Owner | Target |
| --- | --- | --- | --- | --- | --- |
| GAP-01 | WS event schema (3 events) not defined or frozen | IV-2.0.0 | CRITICAL | Chief Architect | 2026-04-29 |
| GAP-02 | UI-Engine Event Binding Contract document does not exist | IV-2.0.0 | CRITICAL | Chief Architect | 2026-04-29 |
| GAP-03 | FastAPI WS endpoint URL and auth mechanism not published to UI team | IV-2.0.0 | HIGH | Backend Lead | 2026-04-28 |
| GAP-04 | DB-INIT-001 not yet run — SQLite schema not confirmed initialized | BJ-010 | CRITICAL | DB Lead | 2026-04-28 |
| GAP-05 | BJ-010 table/field name alignment vs MasterDB v3+ not verified (diff pending) | BJ-010 | HIGH | DB Lead | 2026-04-28 |
| GAP-06 | BJ-010 explicit DB-INIT-001 gating statement missing | BJ-010 | HIGH | DB Lead | 2026-04-28 |
| GAP-07 | CCB-06 (Design Engineer) seat unfilled — gate bypass quorum impossible | CCB | CRITICAL | Program Manager | 2026-04-28 ⚠ OVERDUE |
| GAP-08 | CCB-07 (Document Controller) seat unfilled | CCB | HIGH | Program Manager | 2026-04-28 ⚠ OVERDUE |
| GAP-09 | CCB-08 (Independent Reviewer) seat unfilled | CCB | HIGH | Program Manager | 2026-04-29 ⚠ OVERDUE |
| GAP-10 | CCB weekly standing meeting not scheduled | CCB | HIGH | Chief Architect | 2026-04-28 ⚠ OVERDUE |
| GAP-11 | CCB emergency convene procedure not established | CCB | MODERATE | Program Manager | 2026-04-29 |

# 5. Next Block Readiness

| # | Exit Criterion for Block 3 Closure | Owner | Target | Status |
| --- | --- | --- | --- | --- |
| 1 | GAP-01 CLOSED: WS event schema frozen (all 3 event types defined) | Chief Architect | 2026-04-29 | OPEN |
| 2 | GAP-02 CLOSED: UI-Engine Event Binding Contract signed and published | Chief Architect | 2026-04-29 | OPEN |
| 3 | GAP-03 CLOSED: FastAPI WS endpoint URL + auth published to UI team | Backend Lead | 2026-04-28 | OPEN |
| 4 | GAP-04 CLOSED: DB-INIT-001 PASS confirmed; all UI SQLite bindings unblocked | DB Lead | 2026-04-28 | OPEN |
| 5 | GAP-05 + GAP-06 CLOSED: BJ-010 table/field names confirmed aligned; explicit gating wording added | DB Lead | 2026-04-28 | OPEN |
| 6 | GAP-07 CLOSED: CCB-06 Design Engineer seat named and confirmed | PM | 2026-04-28 | OVERDUE |
| 7 | GAP-08 CLOSED: CCB-07 Document Controller seat named and confirmed | PM | 2026-04-28 | OVERDUE |
| 8 | GAP-09 CLOSED: CCB-08 Independent Reviewer seat named and confirmed | PM | 2026-04-29 | OVERDUE |
| 9 | GAP-10 CLOSED: CCB weekly standing meeting scheduled (recurring invite sent to all 8) | Chief Architect | 2026-04-28 | OVERDUE |
| 10 | R-UI-01 formally closed: CCB-ROSTER-CONFIRMED notice issued by PM | PM | 2026-04-29 | OPEN |
| 11 | B-UI-01 formally closed: IV-2.0.0 integration layer confirmed FROZEN | Chief Architect | 2026-04-29 | OPEN |
| 12 | B-UI-02 formally closed: DB-INIT-001 PASS confirmed | DB Lead | 2026-04-28 | OPEN |

BLOCK 3 CLOSURE VERDICT: NOT READY — 11 of 12 gaps remain open; 4 items already overdue Critical path: GAP-04 (DB-INIT-001) → unblocks all UI SQLite binding; GAP-01/02 (WS schema) → unblocks UI-02/05/07 refresh CCB escalation is the highest-urgency action: R-UI-01 target date has passed. PM must act immediately. Block 4 (Integration Testing / IV-2.0.0) cannot begin until ALL 12 exit criteria are closed. Recommended: Program Manager calls emergency CCB session by 2026-04-28 to force-close CCB gaps.

Lane 3 · Block 3 Agent  |  IFS-BUILD-OUT4-UI-20260424  |  Baseline: MasterDB v3+ · IFS-P7-UI-20260423  |  Generated: 2026-04-27