# OUTPUT 5 — Master Summary, Blocker List & Owner-Wise Coding Action Sheet

| Document ID | IFS-BUILD-OUT5-MASTER-20260424 |
| --- | --- |
| Date | 24 April 2026 |
| Status | ACTIVE — Program Manager / CCB Deliverable |
| Owner | Program Manager |
| Baseline | MasterDB v3+ (Frozen) · TDN-DB-001 Approved |
| Version | 1.0 — Initial Release |

## 1. BUILD EXECUTION SUMMARY

4 build packs have been executed for Saturday deliverables. All outputs are derived from MasterDB v3+ (frozen baseline). No redesign has occurred. All field IDs, rule IDs, module IDs, and schema definitions are preserved verbatim.

| Output | Document ID | Status | Owner | Target Complete |
| --- | --- | --- | --- | --- |
| Output 1 — SQLite Schema Build Execution Pack | IFS-BUILD-OUT1-SCHEMA-20260424 | APPROVED FOR CODING | DB Team Lead | 2026-04-26 |
| Output 2 — Rule Engine Code Execution Pack | IFS-BUILD-OUT2-ENGINE-20260424 | APPROVED FOR CODING | Backend Team Lead | 2026-04-28 |
| Output 3 — Parser Adapter Build Pack | IFS-BUILD-OUT3-PARSER-20260424 | APPROVED FOR CODING | Parser Team Lead | 2026-04-28 |
| Output 4 — UI / Audit Shell Build Pack | IFS-BUILD-OUT4-UI-20260424 | APPROVED FOR CODING | UI/Frontend Team Lead | 2026-04-30 |

## 2. CONSOLIDATED BLOCKER LIST

⛔ 3 ACTIVE PHASE-LEVEL BLOCKERS — None of these may be closed by a team lead unilaterally. All require CCB or Chief Architect decision.

| Blocker ID | Title | Impact | Owner | Target Date | Resolution Required |
| --- | --- | --- | --- | --- | --- |
| BLOCKER-01 | IV-2.0.0 Integration Layer NOT FROZEN | CRITICAL — Parser team cannot finalize write_to_db(); Engine team cannot finalize event contracts; UI team cannot finalize WebSocket schema. All Output 3, Output 4 integration tests blocked. | Chief Architect | 2026-04-29 | Publish frozen IV-2.0.0 specification with all 13 requirements signed off |
| BLOCKER-02 | BJ-010 Concurrency Benchmark NOT EXECUTED | HIGH — SQLite WAL mode performance under simultaneous Parser + Engine write loads unvalidated. Phase 6 deployment risk unknown. Cannot confirm desktop architecture fitness for concurrent use. | QA Lead | 2026-05-03 | Execute all 6 benchmark scenarios A–F; publish PASS/FAIL report; if FAIL → escalate to PostgreSQL migration assessment |
| BLOCKER-03 | CCB Roster NOT CONFIRMED | HIGH — No formal governance authority for Phase 5→6 decisions. Approval workflow screens (UI-07) cannot receive final sign-off. Override quorum rules unenforceable without named approvers. | Program Manager | 2026-04-25 | Name all 8 CCB members with written commitment; publish roster; hold charter meeting |

### 2.1 Team-Level Blockers (Unblocked by Team Leads)

| Blocker ID | Blocks | Resolution |
| --- | --- | --- |
| B-SCHEMA-01 | Output 1: DB-INIT-001 acceptance test | IV-2.0.0 must be frozen (BLOCKER-01) |
| B-ENGINE-01 | Output 2: engine-to-UI event contract | IV-2.0.0 must be frozen (BLOCKER-01) |
| B-ENGINE-02 | Output 2: Engine integration testing | Output 1 DB-INIT-001 must PASS first |
| B-PARSER-01 | Output 3: write_to_db() signature | IV-2.0.0 must be frozen (BLOCKER-01) |
| B-PARSER-02 | Output 3: Parser integration testing | Output 1 DB-INIT-001 must PASS first |
| B-UI-01 | Output 4: WebSocket event schema | IV-2.0.0 must be frozen (BLOCKER-01) |
| B-UI-02 | Output 4: UI SQLite data binding | Output 1 DB-INIT-001 must PASS first |

### 2.2 Risk Register

| Risk ID | Risk | Severity | Owner | Mitigation |
| --- | --- | --- | --- | --- |
| R-01 | Seed data CSV for 196 fields has errors → false UNRESOLVED flags system-wide | HIGH | DB Lead | Pre-validate all seed CSVs against MasterDB v3+ before load; run all 9 count assertions |
| R-02 | ODA File Converter not installed on parser dev machines | MEDIUM | Parser Lead | Install on all machines before CADParser coding; document path |
| R-03 | Tesseract OCR version mismatch / missing language packs | MEDIUM | Parser Lead | Confirm version and language packs before PDFImageParser coding |
| R-04 | S4/S5 hard gate bypassed in code without quorum check | CRITICAL | Backend Lead | Code review gate mandatory; T-ENG-06 unit test must pass |
| R-05 | Audit write missing attributes — R-193 violation at runtime | HIGH | Backend Lead | T-ENG-10 unit test mandatory; 10-attribute validation in AuditWriter |
| R-06 | CCB roster delay beyond 2026-04-25 → Phase 5 sign-off slips | HIGH | Program Manager | Escalate to leadership if confirmation not received by 2026-04-24 |
| R-07 | BJ-010 FAILS → SQLite concurrent write bottleneck on desktop | HIGH | QA Lead + Chief Architect | If FAIL: initiate PostgreSQL migration assessment immediately; do NOT proceed to Phase 6 |

## 3. OWNER-WISE CODING ACTION SHEET

CODING START DATE: Saturday 25 April 2026. Target: All Priority 1 (CRITICAL) tasks complete by 2026-04-28. All Priority 2 (HIGH) tasks complete by 2026-04-30.

### 3.1 DB Team Lead

| Task ID | Task | Priority | Due | Depends On |
| --- | --- | --- | --- | --- |
| A1 | Install SQLite 3.x; validate version >= 3.35 | P1-CRITICAL | 2026-04-25 | — |
| A2 | Write DDL script — all 57 tables in dependency order (Steps 1–20 from Output 1 §3) | P1-CRITICAL | 2026-04-26 | A1 |
| A3 | Apply all 8 PRAGMA settings in connection init function | P1-CRITICAL | 2026-04-26 | A2 |
| A4 | Create 6 immutability triggers (audit tables) + F-006 trigger | P1-CRITICAL | 2026-04-26 | A2 |
| A5 | Create seed CSV/SQL files (Steps 01–20 from Output 1 §6) | P1-CRITICAL | 2026-04-26 | A2 |
| A6 | Execute seed load; run all 9 count assertions | P1-CRITICAL | 2026-04-26 | A5 |
| A7 | Run DB-INIT-001 acceptance test — 57 tables, 293 rules, 196 fields | P1-CRITICAL | 2026-04-26 | A6 |
| A8 | Run DB-INIT-002 acceptance test — immutability verification | P1-CRITICAL | 2026-04-26 | A4 |
| A9 | Hand sealed DB file to Backend Team and Parser Team | P2-HIGH | 2026-04-26 | A7, A8 |
| A10 | Configure Celery beat daily backup task | P2-HIGH | 2026-04-27 | A9 |

### 3.2 Backend Team Lead

| Task ID | Task | Priority | Due | Depends On |
| --- | --- | --- | --- | --- |
| B1 | Implement rule_loader.py — load + sort 293 rules; pass T-ENG-01 | P1-CRITICAL | 2026-04-27 | A7 (DB ready) |
| B2 | Implement audit_writer.py — INSERT-only; 10-attribute validation; T-ENG-10 | P1-CRITICAL | 2026-04-27 | A7 |
| B3 | Implement engine_core.py — ValidationEngine + gate aggregation + S4/S5 hard gate | P1-CRITICAL | 2026-04-27 | B1, B2 |
| B4 | Implement approval_router.py — quorum logic + 28-field prohibited guard | P2-HIGH | 2026-04-28 | A7 |
| B5 | Implement FastAPI WebSocket endpoint (gate status + approval queue push) | P1-CRITICAL | 2026-04-27 | B3 |
| B6 | Code review on all layer modules (B-Schema-01 guard check — no S4/S5 bypass shortcut) | P1-CRITICAL | 2026-04-29 | B3 |

### 3.3 Backend Developer 1

| Task ID | Task | Priority | Due | Depends On |
| --- | --- | --- | --- | --- |
| B-D1-01 | Implement layer_00.py (Source Pre-Check) + layer_01.py (Completeness) | P1-CRITICAL | 2026-04-27 | B1, A7 |
| B-D1-02 | Implement layer_02.py (DataType) + layer_03.py (Unit + F-006 immutability) | P1-CRITICAL | 2026-04-27 | B-D1-01 |
| B-D1-03 | Implement layer_04.py (Enumeration + CV F-191 branch) + layer_05.py (Format) | P1-CRITICAL | 2026-04-28 | B-D1-02 |
| B-D1-04 | Implement severity_handler.py — all 4 severity action paths | P1-CRITICAL | 2026-04-28 | B2 |
| B-D1-05 | Implement blocker_registry.py | P2-HIGH | 2026-04-28 | B-D1-04 |

### 3.4 Backend Developer 2

| Task ID | Task | Priority | Due | Depends On |
| --- | --- | --- | --- | --- |
| B-D2-01 | Implement layer_06.py (Normalisation) + layer_07.py (Dependency Validation) | P1-CRITICAL | 2026-04-27 | B1, A7 |
| B-D2-02 | Implement layer_08.py (Cross-Field) + layer_09.py (Source Governance) | P1-CRITICAL | 2026-04-28 | B-D2-01 |
| B-D2-03 | Implement layer_10.py (Stage Gate) + layer_11.py (Override Governance) | P1-CRITICAL | 2026-04-28 | B-D2-02 |
| B-D2-04 | Implement layer_12.py (Fallback Policy) + fallback_executor.py | P1-CRITICAL | 2026-04-28 | B-D2-03 |
| B-D2-05 | Implement layer_13.py (Geometry Reconciliation — RC-001 to RC-022) | P2-HIGH | 2026-04-29 | B-D2-04 |

### 3.5 Parser Team Lead

| Task ID | Task | Priority | Due | Depends On |
| --- | --- | --- | --- | --- |
| C1 | Implement BaseParser + ParserOutput + FieldExtraction dataclasses | P1-CRITICAL | 2026-04-26 | — |
| C2 | Implement ArchiveExtractor (ZIP + RAR + recursive + encrypted guard) | P1-CRITICAL | 2026-04-27 | C1 |
| C3 | Implement conflict_resolver.py — conflict_rule_master based resolution | P1-CRITICAL | 2026-04-28 | A7, C1 |
| C4 | Implement write_to_db() — field_value_store + field_extraction_log + audit_event_log | P1-CRITICAL | 2026-04-28 | A7, C1, C3 |
| C5 | Run all 12 parser unit tests (T-PARSE-01 to T-PARSE-12) | P2-HIGH | 2026-04-30 | All parser coding complete |
| C6 | Run PARSER-INTAKE-001 and PARSER-FALLBACK-001 acceptance tests | P2-HIGH | 2026-04-30 | C5 |

### 3.6 Parser Developer 1

| Task ID | Task | Priority | Due | Depends On |
| --- | --- | --- | --- | --- |
| C-P1-01 | Implement STAADParser (staad_main + bolt_table + member_table + load + normaliser) | P1-CRITICAL | 2026-04-27 | C1 |
| C-P1-02 | Implement ETABSParser (etabs_main + story + sections + reactions + member mapping) | P2-HIGH | 2026-04-28 | C1 |
| C-P1-03 | Implement CADParser (ODA convert + ezdxf generic geometry) | P2-HIGH | 2026-04-28 | C1 |

### 3.7 Parser Developer 2

| Task ID | Task | Priority | Due | Depends On |
| --- | --- | --- | --- | --- |
| C-P2-01 | Implement MBSParser (mbs_main + geometry + sections + connection + normaliser) | P1-CRITICAL | 2026-04-27 | C1 |
| C-P2-02 | Implement ProtaParser (DXF + PDF combined; FB-RULE-022 guard) | P2-HIGH | 2026-04-28 | C1 |
| C-P2-03 | Implement PDFTextParser (P7; confidence cap 85; PDF_FALLBACK_APPLIED flag) | P2-HIGH | 2026-04-29 | C1 |
| C-P2-04 | Implement PDFImageParser (P8; PyMuPDF + Tesseract; DPI=300; cap 75) | P2-HIGH | 2026-04-29 | C1 |

### 3.8 UI/Frontend Team Lead

| Task ID | Task | Priority | Due | Depends On |
| --- | --- | --- | --- | --- |
| D1 | Implement role-based access control layer (role_master lookup on every screen) | P1-CRITICAL | 2026-04-27 | A7 |
| D2 | Implement UI-02 Stage Status Board + Header Blocker Badge + WebSocket binding | P1-CRITICAL | 2026-04-27 | B5, A7 |
| D3 | Implement UI-07 Approval Queue — quorum guard + APPROVE/REJECT + confirmation modal | P2-HIGH | 2026-04-28 | A7 |
| D4 | Implement UI-09 Source/Confidence Panel (per-field traceability popout) | P2-HIGH | 2026-04-29 | A7 |
| D5 | Run acceptance checklist items 1–15 with QA Lead | P2-HIGH | 2026-04-30 | All UI coding complete |
| D6 | Run UI-BOOTSTRAP-001 + AUDIT-WRITE-001 + APPROVAL-WORKFLOW-001 integration tests | P2-HIGH | 2026-04-30 | D5 |

### 3.9 UI Developer 1

| Task ID | Task | Priority | Due | Depends On |
| --- | --- | --- | --- | --- |
| D-U1-01 | Implement UI-01 Project Dashboard — project create form + file upload + unit immutable warning | P1-CRITICAL | 2026-04-26 | A7 |
| D-U1-02 | Implement UI-03 Field Population Viewer — source/confidence display + prohibited lock icon | P1-CRITICAL | 2026-04-28 | A7, D1 |
| D-U1-03 | Implement UI-08 Audit Trail Viewer — read-only; filter; export; no edit controls | P2-HIGH | 2026-04-28 | A7, D1 |

### 3.10 UI Developer 2

| Task ID | Task | Priority | Due | Depends On |
| --- | --- | --- | --- | --- |
| D-U2-01 | Implement UI-04 Validation Results View + UI-05 Blocker View | P1-CRITICAL | 2026-04-27 | A7, D1 |
| D-U2-02 | Implement UI-06 Override Request View — min-50-char guard + evidence attachment | P2-HIGH | 2026-04-28 | A7, D1 |
| D-U2-03 | Implement UI-10 Manual Review Queue | P2-HIGH | 2026-04-29 | A7, D1 |

### 3.11 QA Lead

| Task ID | Task | Priority | Due | Depends On |
| --- | --- | --- | --- | --- |
| E1 | Run all 15 Engine unit tests (T-ENG-01 to T-ENG-15) on delivery from Backend | P1-CRITICAL | 2026-04-29 | B3, B-D1-05, B-D2-05 |
| E2 | Run all 12 Parser unit tests (T-PARSE-01 to T-PARSE-12) | P2-HIGH | 2026-04-30 | C5 |
| E3 | Run UI acceptance checklist items 1–15 | P2-HIGH | 2026-04-30 | D5 |
| E4 | Run ENGINE-EXEC-001 end-to-end test: mock intake → S1 → S4 gate | P2-HIGH | 2026-04-30 | E1 |
| E5 | Execute BJ-010 concurrency benchmark (6 scenarios A–F) — BLOCKER-02 resolution | P1-CRITICAL | 2026-05-03 | All coding complete |
| E6 | Publish BJ-010 PASS/FAIL report to Chief Architect + Program Manager | P1-CRITICAL | 2026-05-03 | E5 |

### 3.12 Program Manager

| Task ID | Task | Priority | Due |
| --- | --- | --- | --- |
| F1 | Confirm CCB roster — 8 named members with written commitment (BLOCKER-03 resolution) | P1-CRITICAL | 2026-04-25 |
| F2 | Publish CCB charter meeting date; circulate roster to all team leads | P1-CRITICAL | 2026-04-25 |
| F3 | Track daily status against this action sheet; escalate any P1-CRITICAL slippage same day | ONGOING | 2026-04-25 onwards |
| F4 | Confirm Chief Architect availability for IV-2.0.0 sign-off by 2026-04-29 | P1-CRITICAL | 2026-04-25 |
| F5 | Receive BJ-010 report from QA Lead; table for CCB decision if FAIL result | P2-HIGH | 2026-05-03 |
| F6 | Schedule Phase 5 → Phase 6 Go/No-Go decision meeting for 2026-05-06 | P2-HIGH | 2026-04-28 |

### 3.13 IT Admin

| Task ID | Task | Priority | Due | Depends On |
| --- | --- | --- | --- | --- |
| G1 | Install SQLite 3.x on all development machines; validate version >= 3.35 | P1-CRITICAL | 2026-04-25 | — |
| G2 | Install ODA File Converter on all parser development machines; document path | P1-CRITICAL | 2026-04-25 | — |
| G3 | Install Tesseract OCR; confirm English language pack + project language packs | P1-CRITICAL | 2026-04-25 | — |
| G4 | Configure Celery beat daily backup task (once DB is sealed) | P2-HIGH | 2026-04-27 | A9 |
| G5 | Verify no network path for SQLite DB file — must be on local SSD only | P2-HIGH | 2026-04-26 | A7 |

## 4. CRITICAL PATH SUMMARY

| Date | Critical Milestone | Owner | Status |
| --- | --- | --- | --- |
| 2026-04-25 | CCB Roster Confirmed (BLOCKER-03) | Program Manager | PENDING ⚠️ |
| 2026-04-25 | SQLite + ODA + Tesseract installed on all machines | IT Admin | PENDING ⚠️ |
| 2026-04-26 | DB-INIT-001 + DB-INIT-002 PASS — sealed DB handed to Backend & Parser | DB Team Lead | NOT STARTED |
| 2026-04-27 | rule_loader + audit_writer + engine_core + WebSocket endpoint complete | Backend Lead | NOT STARTED |
| 2026-04-27 | STAADParser + MBSParser + BaseParser + ArchiveExtractor complete | Parser Leads | NOT STARTED |
| 2026-04-27 | UI-02 Stage Status Board + Header Blocker Badge live | UI Lead | NOT STARTED |
| 2026-04-28 | All 13 engine layers complete; severity_handler + blocker_registry done | Backend Devs | NOT STARTED |
| 2026-04-28 | All parser adapters complete; conflict_resolver + write_to_db() done | Parser Team | NOT STARTED |
| 2026-04-28 | All 8 primary UI screens implemented; role access layer live | UI Team | NOT STARTED |
| 2026-04-29 | IV-2.0.0 Integration Layer FROZEN (BLOCKER-01) | Chief Architect | PENDING ⚠️ |
| 2026-04-29 | All 15 Engine unit tests PASS (T-ENG-01 to T-ENG-15) | QA Lead | NOT STARTED |
| 2026-04-30 | All 12 Parser tests + 15 UI acceptance criteria PASS | QA Lead | NOT STARTED |
| 2026-05-03 | BJ-010 Concurrency Benchmark EXECUTED + Report published (BLOCKER-02) | QA Lead | NOT STARTED |
| 2026-05-06 | Phase 5 → Phase 6 Go/No-Go Decision (CCB) | Program Manager + CCB | SCHEDULED |

## 5. APPROVAL STATUS — ALL OUTPUTS

| Component | Baseline Authority | Approval Status | Signed By | Date |
| --- | --- | --- | --- | --- |
| MasterDB v3+ (all 57 tables, 196 fields, 293 rules) | IFS-MASTERDB-V3 | FROZEN ✓ | Chief Architect | 2026-04-23 |
| SQLite Technology Decision (TDN-DB-001) | IFS-TDN-DB-001 | APPROVED ✓ | Chief Architect | 2026-04-23 |
| Active Rule Register (293 + 22 RC rules) | IFS-RULE-REG-FINAL-20260423 | FROZEN ✓ | Chief Architect | 2026-04-23 |
| SQLite Schema Build Pack (Output 1) | IFS-BUILD-OUT1-SCHEMA-20260424 | APPROVED FOR CODING ✓ | DB Team Lead | 2026-04-24 |
| Rule Engine Code Pack (Output 2) | IFS-BUILD-OUT2-ENGINE-20260424 | APPROVED FOR CODING ✓ | Backend Team Lead | 2026-04-24 |
| Parser Adapter Build Pack (Output 3) | IFS-BUILD-OUT3-PARSER-20260424 | APPROVED FOR CODING ✓ | Parser Team Lead | 2026-04-24 |
| UI Shell Build Pack (Output 4) | IFS-BUILD-OUT4-UI-20260424 | APPROVED FOR CODING ✓ | UI Team Lead | 2026-04-24 |
| IV-2.0.0 Integration Layer Spec | Pending | NOT FROZEN ⛔ | Chief Architect | By 2026-04-29 |
| BJ-010 Concurrency Benchmark | Pending | NOT EXECUTED ⛔ | QA Lead | By 2026-05-03 |
| CCB Charter + Roster | Pending | NOT CONFIRMED ⛔ | Program Manager | By 2026-04-25 |